## Summary
#VALUE!
Summary
#VALUE!
Count of Jobs: | 0
Job # | Contract | Customer | Project Manager | Estimator | Department | Closed Status | Base Contract | Approved Change Orders | (Work Done ) Outstanding Change Orders | Outstanding Allowance | Adjusted Contract Price | Estimated Total Direct Costs | QU Original Budget | CO Change Order Budget | Original GP | Change Order GP | Total Direct Budget | Over/Under Budget | Budgeted Gross Profit (Loss) | Estimated Gross Profit (Loss) | Estimated GP % | Current GP % | Prior Month1 GP | Variance Month1 GP | Prior Month2 GP | Variance Month2 GP | Prior Month3 GP | Variance Month3 GP | Direct Cost To Date | % Complete | Total Gross Profit Recognized To Date | Gross Profit Recognized Prior Years | Gross Profit (Loss) Recognized This Year | Total Amount Billed To Date | Remaining Billing Amount | Current Retainage Amount | Retainage % Held | Cash Received | Net Cash Flow | Costs and Estimated Earnings In Excess Of Billings | Billings In Excess Of Costs And Estimated Earnings | Prior Year Incurred Cost | Prior Year Billing | AR | AR Retainage | AP | AP Retainage | Last Projection Date
21-1001- | CT DOT 108-0186 McNamee Construction Corp. | McNamee Construction Corp. |  |  | CONNECTICUT | Y | 1386800 | 138412.82 | 0 |  | 1525212.82 | 1092176 | 1097168 | 93510.05 | 0 | 0 | 1190678.05 | 0 | 0 | 0 | 0 | 0 | 0.78066 | 0 | 0.78066 | 0 | 0.78066 | 0 | 1092176 | 0 | 0 | 0 | 0 | 1525212.82 | 0 | 0 | 0 | 1525212.82 | 0 | 0 | 0 | 0 | 0 | 0 | 1525212.82 | 0 | 0 | 2023-09-06
21-1002- | CT DOT 51-272-R1 McNamee Construction Corp | McNamee Construction Corp. |  |  | CONNECTICUT | Y | 667388.43 | 1960164.17 | 0 |  | 2643464 | 1699645 | 546640 | 1153005 | 0 | 0 | 1699645 | 0 | 0 | 0 | 0 | 0 | 0.64685 | 0 | 0.64685 | 0 | 0.64685 | 0 | 1168147.67 | 0 | 0 | 0 | 0 | 2627552.6 | 0 | 0 | 0 | 2627552.6 | 0 | 0 | 0 | 4366.87 | 94021.49 | 0 | 2627552.6 | 12621.48 | 0 | 2024-08-07
21-1003- | CT DOT 163-196 McNamee Construction Corp | McNamee Construction Corp. |  |  | CONNECTICUT | Y | 1095500 | 1586695.79 | 0 |  | 2682195.79 | 2066263.1 | 876400 | 847362.26 | 0 | 0 | 1723762.26 | 0 | 0 | 0 | 0 | 0 | 0.64267 | 0 | 0.64267 | 0 | 0.64267 | 0 | 2065962.78 | 0 | 0 | 0 | 0 | 2682195.79 | 0 | 0 | 0 | 2682195.79 | 0 | 0 | 0 | 672806.02 | 777217.38 | 0 | 2682195.79 | 240289.36 | 0 | 2025-03-18
21-1004- | CT COT 78-092 McNamee Construction Corp | McNamee Construction Corp. |  |  | CONNECTICUT | Y | 270080 | 0 | 0 |  | 270080 | 229213.54 | 216670.4 | 0 | 0 | 0 | 216670.4 | 0 | 0 | 0 | 0 | 0 | 0.80224 | 0 | 0.80224 | 0 | 0.80224 | 0 | 229213.54 | 0 | 0 | 0 | 0 | 270080 | 0 | 0 | 0 | 270080 | 0 | 0 | 0 | 0 | 750 | 0 | 270080 | 0 | 0 | 2023-09-06
21-1005- | CT DOT 63-719 Rotha Contracting Co., Inc. | Rotha Contracting Co., Inc. |  |  | CONNECTICUT | Y | 920079 | 22237.44 | 0 |  | 942316.44 | 692639.17 | 736063.2 | 0 | 0 | 0 | 736063.2 | 0 | 0 | 0 | 0 | 0 | 0.78112 | 0 | 0.78112 | 0 | 0.78112 | 0 | 692639.17 | 0 | 0 | 0 | 0 | 942316.44 | 0 | 0 | 0 | 942316.44 | 0 | 0 | 0 | 52094.99 | 46706.57 | 0 | 942316.44 | 6889.54 | 0 | 2025-03-18
21-1006- | CT DOT 42-0325 New England Infrastructure, Inc. | New England Infrastructure, Inc. |  |  | CONNECTICUT | Y | 83725 | 0 | 0 |  | 83725 | 61242.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61242.88 | 0 | 0 | 0 | 0 | 83725 | 0 | 0 | 0 | 83725 | 0 | 0 | 0 | 0 | 0 | 0 | 83725 | 0 | 0 | 2024-03-05
21-1007- | CT DOT 146-199 Town of Vernon | Town of Vernon |  |  | CONNECTICUT | Y | 150000 | 20300 | 0 |  | 170300 | 74344.1 | 0 | 15100 | 0 | 0 | 15100 | 0 | 0 | 0 | 0 | 0 | 0.088667 | 0 | 0.088667 | 0 | 0.088667 | 0 | 74344.1 | 0 | 0 | 0 | 0 | 170300 | 0 | 0 | 0 | 170300 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 0 | 2025-03-18
21-1008- | CT DOT 83-267 Mohawk Northeast, Inc. | Mohawk Northeast, Inc. |  |  | CONNECTICUT | Y | 418500 | -13050 | 0 |  | 405450 | 197359.43 | 334800 | -135538 | 0 | 0 | 199262 | 0 | 0 | 0 | 0 | 0 | 0.49146 | 0 | 0.49146 | 0 | 0.49146 | 0 | 197359.43 | 0 | 0 | 0 | 0 | 405450 | 0 | 0 | 0 | 405450 | 0 | 0 | 0 | 54537.51 | 265099.6 | 0 | 405450 | 0 | 0 | 2025-03-18
21-1009- | HT.224.130 HOLLAND TUNNEL / TULLY CONST. | Tully Construction Co., Inc. |  |  | NEW YORK | N | 2730505 | 196964.64 | 0 |  | 2906972 | 2322882 | 2243954.42 | 78928 | 0 | 0 | 2322882.42 | 0 | 0 | 0 | 0 | 0 | 0.79348 | 0 | 0.79348 | 0 | 0.79348 | 0 | 1626089.07 | 0 | 0 | 0 | 0 | 1679142.74 | 0 | 83957.15 | 0 | 1256708.31 | 0 | 0 | 0 | 1893.92 | 0 | 338477.28 | 1256708.31 | 10332.79 | 0 | 2025-03-18
21-1009- A | Holland Tunnel Extra Work / Slade Industries | Slade Industries, Inc. |  |  | NEW YORK | N | 22818.73 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1249.04 | 0 | 0 | 0 | 0 | 22818.73 | 0 | 0 | 0 | 22818.73 | 0 | 0 | 0 | 0 | 0 | 0 | 22818.73 | 0 | 0 | 2025-03-18
21-1010- | NY Valhalla Boiler Tank | Vahalla Tank |  |  | NEW YORK | Y | 52500 | 12400 | 0 |  | 64900 | 22247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22247 | 0 | 0 | 0 | 0 | 64900 | 0 | 0 | 0 | 64900 | 0 | 0 | 0 | 0 | 0 | 0 | 64900 | 0 | 0 | 2023-09-06
21-1011- | NYS DOT #D264563 - HEMPSTEAD - H&L CONT. | H & L Contracting, LLC |  |  | NEW YORK | Y | 478000 | -91775.53 | 0 |  | 386224 | 705323.58 | 346500 | 0 | 0 | 0 | 346500 | 0 | 0 | 0 | 0 | 0 | 0.89715 | 0 | 0.89715 | 0 | 0.89715 | 0 | 705323.58 | 0 | 0 | 0 | 0 | 386224.47 | 0 | 0 | 0 | 386224.47 | 0 | 0 | 0 | 299968.15 | 163195.32 | 0 | 386224.47 | 44490.23 | 0 | 2025-03-18
21-1013- | CT DOT 0096-0200 Waters Construction Co. | Waters Construction Co. |  |  | CONNECTICUT | Y | 244225.34 | 0 | 0 |  | 244225.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244225.34 | 0 | 0 | 0 | 244225.34 | 0 | 0 | 0 | 0 | 0 | 0 | 244225.34 | 0 | 0
21-1014- | NR-42 Gas Holder NYC 2017-4 Welkin Construction | Welkin Mechanical, LLC |  |  | NEW YORK | Y | 12019 | 0 | 0 |  | 12019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12018.98 | 0 | 0 | 0 | 12018.98 | 0 | 0 | 0 | 0 | 0 | 0 | 12018.98 | 0 | 0
21-1015- | CT DOT 63-0654 Mohawn Northeast, Inc. | Mohawk Northeast, Inc. |  |  | CONNECTICUT | Y | 425000 | 0 | 0 |  | 425000 | 321840.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321840.71 | 0 | 0 | 0 | 0 | 425000 | 0 | 0 | 0 | 425000 | 0 | 0 | 0 | 0 | 0 | 0 | 425000 | 0 | 0 | 2023-09-06
21-1016- | Missouri Substation Painting Fort Kickapoo Substation |  |  |  | MISSOURI | Y | 91980 | 9500 | 0 |  | 101480 | 48804.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48804.98 | 0 | 0 | 0 | 0 | 101480 | 0 | 0 | 0 | 101480 | 0 | 0 | 0 | 0 | 0 | 0 | 101480 | 0 | 0 | 2021-12-31
21-1017- | CT DOT 0154-0125 - ARBORIO CORP | ARBORIO COROPORATION |  |  | CONNECTICUT | Y | 352000 | 33812.04 | 0 |  | 385812.04 | 219653.46 | 287820 | 24384.98 | 0 | 0 | 312204.98 | 0 | 0 | 0 | 0 | 0 | 0.80922 | 0 | 0.80922 | 0 | 0.80922 | 0 | 219653.46 | 0 | 0 | 0 | 0 | 385812.04 | 0 | 0 | 0 | 385812.04 | 0 | 0 | 0 | 0 | 1290 | 0 | 385812.04 | 10458.67 | 0 | 2023-09-06
21-1018- | HUNT'S POINT - DEAN ENERGY SOLUTIONS | DEAN ENERGY SOLUTIONS |  |  | NEW YORK | Y | 30000 | 0 | 0 |  | 30000 | 15209.84 | 21000 | 0 | 0 | 0 | 21000 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0 | 0.7 | 0 | 0.7 | 0 | 15209.84 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 2023-12-07
21-1019- | SIGNATURE BRIDGE NJDOT - CMC | COMMODORE MAINTENANCE CORP |  |  | NEW JERSEY | Y | 5100000 | 930000 | 0 |  | 6030000 | 4374347.6 | 4743000 | 0 | 0 | 0 | 4743000 | 0 | 0 | 0 | 0 | 0 | 0.78657 | 0 | 0.78657 | 0 | 0.78657 | 0 | 4371438.65 | 0 | 0 | 0 | 0 | 6030000 | 0 | 0 | 0 | 6030000 | 0 | 0 | 0 | 2843279.41 | 4155420 | 0 | 6030000 | 283687.42 | 0 | 2025-03-18
21-1020- | NY 17-530 REHAB VARIOUS BRIDGES WESTCHESTER - LAURA | LAURA LI INDUSTRIES |  |  | NEW YORK | Y | 133850 | 400 | 0 |  | 134250 | 21695.28 | 100850 | 0 | 0 | 0 | 100850 | 0 | 0 | 0 | 0 | 0 | 0.75121 | 0 | 0.75121 | 0 | 0.75121 | 0 | 21695.28 | 0 | 0 | 0 | 0 | 134250 | 0 | 0 | 0 | 134250 | 0 | 0 | 0 | 0 | 0 | 0 | 134250 | 0 | 0 | 2023-12-07
21-1021- | MA DOT #117036 - Interstate 90 Bridges - MIG CORP. | MIG CORPORATION, INC. |  |  | MASSACHUSETTS | N | 1200000 | 61306.28 | 0 |  | 1215635 | 1685651 | 1020000 | 28621.07 | 0 | 0 | 1048621.07 | 0 | 0 | 0 | 0 | 0 | 0.83138 | 0 | 0.83138 | 0 | 0.83138 | 0 | 1688209.37 | 0 | 0 | 0 | 0 | 1251681.28 | 0 | 0 | 0 | 1212741.02 | 0 | 0 | 0 | 1514692.75 | 1094760.26 | 38940.26 | 1212741.02 | 98783.5 | 0 | 2024-08-01
22-1001- | CRANES AT HOLTSVILLE GT - NATIONAL GRID | National Grid |  |  | NEW YORK | Y | 141400 | -8000 | 0 |  | 133400 | 201907.89 | 120190 | 0 | 0 | 0 | 120190 | 0 | 0 | 0 | 0 | 0 | 0.90097 | 0 | 0.90097 | 0 | 0.90097 | 0 | 201907.89 | 0 | 0 | 0 | 0 | 133400 | 0 | 0 | 0 | 133400 | 0 | 0 | 0 | 0 | 0 | 0 | 133400 | 6300.34 | 0 | 2023-09-06
22-1002- | H-STREET BRIDGE REHABILITATION - MCNAMEE - PV | McNamee Construction Corp. |  |  | NEW YORK | Y | 51625 | 0 | 0 |  | 50150 | 19522.76 | 43300 | 0 | 0 | 0 | 43300 | 0 | 0 | 0 | 0 | 0 | 0.83874 | 0 | 0.83874 | 0 | 0.83874 | 0 | 19522.76 | 0 | 0 | 0 | 0 | 50150 | 0 | 0 | 0 | 50150 | 0 | 0 | 0 | 2584.39 | 18175 | 0 | 50150 | 0 | 0 | 2025-03-18
22-1003- | MOUNT OLIVE, NJ - LEAD PAINT REMOVAL ON WATER TANK - EBI | EBI Consulting |  |  | NEW JERSEY | Y | 32600 | 0 | 0 |  | 32600 | 8332.41 | 28468 | 0 | 0 | 0 | 28468 | 0 | 0 | 0 | 0 | 0 | 0.87325 | 0 | 0.87325 | 0 | 0.87325 | 0 | 7950.47 | 0 | 0 | 0 | 0 | 32600 | 0 | 0 | 0 | 32600 | 0 | 0 | 0 | 5283.45 | 0 | 0 | 32600 | 0 | 0 | 2023-12-07
22-1004- | CT DOT 0040-0141 / HADDAM / AMER. BRDGE. | American Bridge Co. |  |  | CONNECTICUT | N | 3102105.09 | 718853.93 | 0 |  | 3711343 | 2968091.74 | 2288568 | 741524.5 | 0 | 0 | 3030092.5 | 0 | 0 | 0 | 0 | 0 | 0.79302 | 0 | 0.79644 | 0 | 0.80713 | 0 | 3519004.46 | 0 | 0 | 0 | 0 | 3765599.02 | 0 | 0 | 0 | 3341942.46 | 0 | 0 | 0 | 2481569.24 | 2471080 | 423656.56 | 3341942.46 | 232821.44 | 0 | 2024-08-05
22-1005- | RI DOT / #2022CB046 / AETNA BRIDGE CO. | Aetna Bridge Company |  |  | RHODE ISLAND | Y | 855500 | 0 | 0 |  | 855500 | 489122.54 | 641250 | 0 | 0 | 0 | 641250 | 0 | 0 | 0 | 0 | 0 | 0.74956 | 0 | 0.74956 | 0 | 0.74956 | 0 | 489122.54 | 0 | 0 | 0 | 0 | 855500 | 0 | 0 | 0 | 855500 | 0 | 0 | 0 | 474742.46 | 827637.5 | 0 | 855500 | 19110.03 | 0 | 2025-03-18
22-1006- | CT DOT 165-509 / WINDSOR LOCKS / ROTHA | Rotha Contracting Co., Inc. |  |  | CONNECTICUT | N | 2228730 | 66000 | 0 |  | 2227040 | 2350000 | 1760000 | 0 | 0 | 0 | 1760000 | 0 | 0 | 0 | 0 | 0 | 0.76697 | 0 | 0.76697 | 0 | 0.76754 | 0 | 2263874.11 | 0 | 0 | 0 | 0 | 1786640.37 | 0 | 0 | 0 | 1712892.37 | 0 | 0 | 0 | 1352597.75 | 1230339.8 | 73748 | 1712892.37 | 97893.49 | 0 | 2024-08-07
22-1007- | RFK BRIDGE / COMMODORE MAINT. | COMMODORE MAINTENANCE CORP |  |  | NEW YORK | Y | 1850000 | 0 | 0 |  | 1850000 | 1678795.86 | 1354000 | 0 | 0 | 0 | 1354000 | 0 | 0 | 0 | 0 | 0 | 0.73189 | 0 | 0.73189 | 0 | 0.73189 | 0 | 1678795.86 | 0 | 0 | 0 | 0 | 1850000 | 0 | 0 | 0 | 1850000 | 0 | 0 | 0 | 1678795.86 | 1850000 | 0 | 1850000 | 72155.75 | 0 | 2025-03-18
22-1008- | CT DOT 170-3557 / MCNAMEE | McNamee Construction Corp. |  |  | CONNECTICUT | N | 1450000 | -149294.02 | 0 |  | 1096000 | 746280 | 987000 | -90720 | 0 | 0 | 896280 | 0 | 0 | 0 | 0 | 0 | 0.68907 | 0 | 0.68907 | 0 | 0.68907 | 0 | 644277.24 | 0 | 0 | 0 | 0 | 863555.98 | 0 | 0 | 0 | 861555.98 | 0 | 0 | 0 | 446657.61 | 681000 | 2000 | 861555.98 | 54206.91 | 0 | 2024-08-05
22-1009- | CT DOT 170-3551 / ROTHA | Rotha Contracting Co., Inc. |  |  | CONNECTICUT | N | 712300 | 0 | 0 |  | 712300 | 530000 | 530000 | 0 | 0 | 0 | 530000 | 0 | 0 | 0 | 0 | 0 | 0.74407 | 0 | 0.74407 | 0 | 0.74407 | 0 | 241053.47 | 0 | 0 | 0 | 0 | 353990 | 0 | 0 | 0 | 353990 | 0 | 0 | 0 | 59897.2 | 163000 | 0 | 353990 | 33744.73 | 0 | 2023-06-27
22-1010- | CT DOT 0171-0484 / BEAM END REPAIRS / MCNAMEE | McNamee Construction Corp. |  |  | CONNECTICUT | N | 1372941 | 132225.95 | 0 |  | 1409661 | 1005000 | 1005000 | 49160 | 0 | 0 | 1054160 | 0 | 0 | 0 | 0 | 0 | 0.70036 | 0 | 0.70036 | 0 | 0.70036 | 0 | 957003.1 | 0 | 0 | 0 | 0 | 1380347.55 | 0 | 0 | 0 | 1380347.55 | 0 | 0 | 0 | 280471.99 | 431370.1 | 0 | 1380347.55 | 19068.19 | 0 | 2023-06-27
22-1095- | BRIDGE PAINTING OF SEVEN BRIDGES - CMC - PETER | COMMODORE MAINTENANCE CORP |  |  | NEW YORK | Y | 288000 | 0 | 0 |  | 288000 | 421130.4 | 240000 | 0 | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0.83333 | 0 | 0.83333 | 0 | 0.83333 | 0 | 421130.4 | 0 | 0 | 0 | 0 | 288000 | 0 | 0 | 0 | 288000 | 0 | 0 | 0 | -3287.01 | 0 | 0 | 288000 | 0 | 0 | 2025-03-18
23-1000- | NYC DOT HB1070QN / BREWER & CROSS BAY / COMMODORE | COMMODORE CONSTRUCTION CORP |  |  | NEW YORK | N | 2300000 | 0 | 0 |  | 2300000 | 1910000 | 1910000 | 0 | 0 | 0 | 1910000 | 0 | 0 | 0 | 0 | 0 | 0.83043 | 0 | 0.83043 | 0 | 0.83043 | 0 | 2156357.25 | 0 | 0 | 0 | 0 | 1330388.29 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 29605.87 | 25000 | 1210388.29 | 120000 | 264937.76 | 0 | 2025-03-13
23-1001- | NYPA COOLING TOWER / MACAN DEVE | MACAN DEVE ENGINEERS, DPC |  |  | NEW YORK | Y | 126000 | 1425 | 0 |  | 127425 | 63404.37 | 72500 | 0 | 0 | 0 | 72500 | 0 | 0 | 0 | 0 | 0 | 0.56896 | 0 | 0.56896 | 0 | 0.56896 | 0 | 63404.37 | 0 | 0 | 0 | 0 | 127425 | 0 | 0 | 0 | 127425 | 0 | 0 | 0 | 58781.34 | 126000 | 0 | 127425 | 0 | 0 | 2025-03-18
23-1002- | MA DOT #122517 - TEWKSBURY - NEL CORP. | NEL Corp. |  |  | MASSACHUSETTS | N | 2416210 | 0 | 0 |  | 2416210 | 1720948 | 1720948 | 0 | 0 | 0 | 1720948 | 0 | 0 | 0 | 0 | 0 | 0.71225 | 0 | 0.71225 | 0 | 0.71225 | 0 | 14782.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5252.5 | 0 | 0 | 0 | 6895.2 | 0 | 2024-08-02
24-1001- | RK-19A / CMC / RFK BRIDGE PLATFORM | COMMODORE MAINTENANCE CORP |  |  | NEW YORK | N | 10000000 | 0 | 0 |  | 13700000 | 16943960 | 6621980 | 0 | 0 | 0 | 6621980 | 0 | 0 | 0 | 0 | 0 | 0.6622 | 0 | 0.6622 | 0 | 0.6622 | 0 | 3925411.39 | 0 | 0 | 0 | 0 | 5702625 | 0 | 0 | 0 | 4654000 | 0 | 0 | 0 | 0 | 0 | 1048625 | 4654000 | 113467.12 | 0 | 2025-03-13
24-1002- | NYC DDC / HWK1669A / JRCRUZ | JRCRUZ Corp. |  |  | NEW YORK | N | 617796 | 0 | 0 |  | 617796 | 94568 | 368315.2 | 0 | 0 | 0 | 368315.2 | 0 | 0 | 0 | 0 | 0 | 0.59618 | 0 | 0.59618 | 0 | 0.59618 | 0 | 94567.55 | 0 | 0 | 0 | 0 | 617796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617796 | 0 | 22379.35 | 0 | 2025-03-13
24-1003- | RI DOT 2024CB018 / AETNA BRIDGE / LAFAYETTE BRIDGE REPAIRS | Aetna Bridge Company |  |  | RHODE ISLAND | N | 513955.56 | 0 | 0 |  | 513955.56 | 300409.78 | 300409.78 | 0 | 0 | 0 | 300409.78 | 0 | 0 | 0 | 0 | 0 | 0.58451 | 0 | 0.58451 | 0 | 0.58451 | 0 | 54454.99 | 0 | 0 | 0 | 0 | 262966.58 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 212966.58 | 50000 | 15123.81 | 0 | 2025-03-13
24-1004- | Emergency Repairs / Willimantic | McNamee Construction Corp. |  |  | CONNECTICUT | N | 251517.42 | 0 | 0 |  | 251517.42 | 52830 | 183260 | 0 | 0 | 0 | 183260 | 0 | 0 | 0 | 0 | 0 | 0.72862 | 0 | 0 | 0 | 0 | 0 | 52829.68 | 0 | 0 | 0 | 0 | 150910.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150910.45 | 0 | 2554.68 | 0 | 2025-03-13
Grand Totals:

## Completed Contracts
#VALUE!
Summary
#VALUE!
Count of Jobs: | 0
Job # | Contract | Customer | Project Manager | Estimator | Department | Closed Status | Base Contract | Approved Change Orders | (Work Done ) Outstanding Change Orders | Outstanding Allowance | Adjusted Contract Price | Estimated Total Direct Costs | QU Original Budget | CO Change Order Budget | Original GP | Change Order GP | Total Direct Budget | Over/Under Budget | Budgeted Gross Profit (Loss) | Estimated Gross Profit (Loss) | Estimated GP % | Current GP % | Prior Month1 GP | Variance Month1 GP | Prior Month2 GP | Variance Month2 GP | Prior Month3 GP | Variance Month3 GP | Direct Cost To Date | % Complete | Total Gross Profit Recognized To Date | Gross Profit Recognized Prior Years | Gross Profit (Loss) Recognized This Year | Total Amount Billed To Date | Remaining Billing Amount | Current Retainage Amount | Retainage % Held | Cash Received | Net Cash Flow | Costs and Estimated Earnings In Excess Of Billings | Billings In Excess Of Costs And Estimated Earnings | Prior Year Incurred Cost | Prior Year Billing | AR | AR Retainage | AP | AP Retainage | Last Projection Date
21-1001- | CT DOT 108-0186 McNamee Construction Corp. | McNamee Construction Corp. |  |  | CONNECTICUT | Y | 1386800 | 138412.82 | 0 |  | 1525212.82 | 1092176 | 1097168 | 93510.05 | 0 | 0 | 1190678.05 | 0 | 0 | 0 | 0 | 0 | 0.78066 | 0 | 0.78066 | 0 | 0.78066 | 0 | 1092176 | 0 | 0 | 0 | 0 | 1525212.82 | 0 | 0 | 0 | 1525212.82 | 0 | 0 | 0 | 0 | 0 | 0 | 1525212.82 | 0 | 0 | 2023-09-06
21-1004- | CT COT 78-092 McNamee Construction Corp | McNamee Construction Corp. |  |  | CONNECTICUT | Y | 270080 | 0 | 0 |  | 270080 | 229213.54 | 216670.4 | 0 | 0 | 0 | 216670.4 | 0 | 0 | 0 | 0 | 0 | 0.80224 | 0 | 0.80224 | 0 | 0.80224 | 0 | 229213.54 | 0 | 0 | 0 | 0 | 270080 | 0 | 0 | 0 | 270080 | 0 | 0 | 0 | 0 | 750 | 0 | 270080 | 0 | 0 | 2023-09-06
21-1005- | CT DOT 63-719 Rotha Contracting Co., Inc. | Rotha Contracting Co., Inc. |  |  | CONNECTICUT | Y | 920079 | 22237.44 | 0 |  | 942316.44 | 692639.17 | 736063.2 | 0 | 0 | 0 | 736063.2 | 0 | 0 | 0 | 0 | 0 | 0.78112 | 0 | 0.78112 | 0 | 0.78112 | 0 | 692639.17 | 0 | 0 | 0 | 0 | 942316.44 | 0 | 0 | 0 | 942316.44 | 0 | 0 | 0 | 52094.99 | 46706.57 | 0 | 942316.44 | 6889.54 | 0 | 2025-03-18
21-1006- | CT DOT 42-0325 New England Infrastructure, Inc. | New England Infrastructure, Inc. |  |  | CONNECTICUT | Y | 83725 | 0 | 0 |  | 83725 | 61242.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61242.88 | 0 | 0 | 0 | 0 | 83725 | 0 | 0 | 0 | 83725 | 0 | 0 | 0 | 0 | 0 | 0 | 83725 | 0 | 0 | 2024-03-05
21-1007- | CT DOT 146-199 Town of Vernon | Town of Vernon |  |  | CONNECTICUT | Y | 150000 | 20300 | 0 |  | 170300 | 74344.1 | 0 | 15100 | 0 | 0 | 15100 | 0 | 0 | 0 | 0 | 0 | 0.088667 | 0 | 0.088667 | 0 | 0.088667 | 0 | 74344.1 | 0 | 0 | 0 | 0 | 170300 | 0 | 0 | 0 | 170300 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 0 | 2025-03-18
21-1008- | CT DOT 83-267 Mohawk Northeast, Inc. | Mohawk Northeast, Inc. |  |  | CONNECTICUT | Y | 418500 | -13050 | 0 |  | 405450 | 197359.43 | 334800 | -135538 | 0 | 0 | 199262 | 0 | 0 | 0 | 0 | 0 | 0.49146 | 0 | 0.49146 | 0 | 0.49146 | 0 | 197359.43 | 0 | 0 | 0 | 0 | 405450 | 0 | 0 | 0 | 405450 | 0 | 0 | 0 | 54537.51 | 265099.6 | 0 | 405450 | 0 | 0 | 2025-03-18
21-1010- | NY Valhalla Boiler Tank | Vahalla Tank |  |  | NEW YORK | Y | 52500 | 12400 | 0 |  | 64900 | 22247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22247 | 0 | 0 | 0 | 0 | 64900 | 0 | 0 | 0 | 64900 | 0 | 0 | 0 | 0 | 0 | 0 | 64900 | 0 | 0 | 2023-09-06
21-1015- | CT DOT 63-0654 Mohawn Northeast, Inc. | Mohawk Northeast, Inc. |  |  | CONNECTICUT | Y | 425000 | 0 | 0 |  | 425000 | 321840.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321840.71 | 0 | 0 | 0 | 0 | 425000 | 0 | 0 | 0 | 425000 | 0 | 0 | 0 | 0 | 0 | 0 | 425000 | 0 | 0 | 2023-09-06
21-1016- | Missouri Substation Painting Fort Kickapoo Substation |  |  |  | MISSOURI | Y | 91980 | 9500 | 0 |  | 101480 | 48804.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48804.98 | 0 | 0 | 0 | 0 | 101480 | 0 | 0 | 0 | 101480 | 0 | 0 | 0 | 0 | 0 | 0 | 101480 | 0 | 0 | 2021-12-31
21-1017- | CT DOT 0154-0125 - ARBORIO CORP | ARBORIO COROPORATION |  |  | CONNECTICUT | Y | 352000 | 33812.04 | 0 |  | 385812.04 | 219653.46 | 287820 | 24384.98 | 0 | 0 | 312204.98 | 0 | 0 | 0 | 0 | 0 | 0.80922 | 0 | 0.80922 | 0 | 0.80922 | 0 | 219653.46 | 0 | 0 | 0 | 0 | 385812.04 | 0 | 0 | 0 | 385812.04 | 0 | 0 | 0 | 0 | 1290 | 0 | 385812.04 | 10458.67 | 0 | 2023-09-06
21-1018- | HUNT'S POINT - DEAN ENERGY SOLUTIONS | DEAN ENERGY SOLUTIONS |  |  | NEW YORK | Y | 30000 | 0 | 0 |  | 30000 | 15209.84 | 21000 | 0 | 0 | 0 | 21000 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0 | 0.7 | 0 | 0.7 | 0 | 15209.84 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 2023-12-07
21-1020- | NY 17-530 REHAB VARIOUS BRIDGES WESTCHESTER - LAURA | LAURA LI INDUSTRIES |  |  | NEW YORK | Y | 133850 | 400 | 0 |  | 134250 | 21695.28 | 100850 | 0 | 0 | 0 | 100850 | 0 | 0 | 0 | 0 | 0 | 0.75121 | 0 | 0.75121 | 0 | 0.75121 | 0 | 21695.28 | 0 | 0 | 0 | 0 | 134250 | 0 | 0 | 0 | 134250 | 0 | 0 | 0 | 0 | 0 | 0 | 134250 | 0 | 0 | 2023-12-07
22-1001- | CRANES AT HOLTSVILLE GT - NATIONAL GRID | National Grid |  |  | NEW YORK | Y | 141400 | -8000 | 0 |  | 133400 | 201907.89 | 120190 | 0 | 0 | 0 | 120190 | 0 | 0 | 0 | 0 | 0 | 0.90097 | 0 | 0.90097 | 0 | 0.90097 | 0 | 201907.89 | 0 | 0 | 0 | 0 | 133400 | 0 | 0 | 0 | 133400 | 0 | 0 | 0 | 0 | 0 | 0 | 133400 | 6300.34 | 0 | 2023-09-06
22-1002- | H-STREET BRIDGE REHABILITATION - MCNAMEE - PV | McNamee Construction Corp. |  |  | NEW YORK | Y | 51625 | 0 | 0 |  | 50150 | 19522.76 | 43300 | 0 | 0 | 0 | 43300 | 0 | 0 | 0 | 0 | 0 | 0.83874 | 0 | 0.83874 | 0 | 0.83874 | 0 | 19522.76 | 0 | 0 | 0 | 0 | 50150 | 0 | 0 | 0 | 50150 | 0 | 0 | 0 | 2584.39 | 18175 | 0 | 50150 | 0 | 0 | 2025-03-18
22-1005- | RI DOT / #2022CB046 / AETNA BRIDGE CO. | Aetna Bridge Company |  |  | RHODE ISLAND | Y | 855500 | 0 | 0 |  | 855500 | 489122.54 | 641250 | 0 | 0 | 0 | 641250 | 0 | 0 | 0 | 0 | 0 | 0.74956 | 0 | 0.74956 | 0 | 0.74956 | 0 | 489122.54 | 0 | 0 | 0 | 0 | 855500 | 0 | 0 | 0 | 855500 | 0 | 0 | 0 | 474742.46 | 827637.5 | 0 | 855500 | 19110.03 | 0 | 2025-03-18
22-1007- | RFK BRIDGE / COMMODORE MAINT. | COMMODORE MAINTENANCE CORP |  |  | NEW YORK | Y | 1850000 | 0 | 0 |  | 1850000 | 1678795.86 | 1354000 | 0 | 0 | 0 | 1354000 | 0 | 0 | 0 | 0 | 0 | 0.73189 | 0 | 0.73189 | 0 | 0.73189 | 0 | 1678795.86 | 0 | 0 | 0 | 0 | 1850000 | 0 | 0 | 0 | 1850000 | 0 | 0 | 0 | 1678795.86 | 1850000 | 0 | 1850000 | 72155.75 | 0 | 2025-03-18
22-1095- | BRIDGE PAINTING OF SEVEN BRIDGES - CMC - PETER | COMMODORE MAINTENANCE CORP |  |  | NEW YORK | Y | 288000 | 0 | 0 |  | 288000 | 421130.4 | 240000 | 0 | 0 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0.83333 | 0 | 0.83333 | 0 | 0.83333 | 0 | 421130.4 | 0 | 0 | 0 | 0 | 288000 | 0 | 0 | 0 | 288000 | 0 | 0 | 0 | -3287.01 | 0 | 0 | 288000 | 0 | 0 | 2025-03-18
23-1001- | NYPA COOLING TOWER / MACAN DEVE | MACAN DEVE ENGINEERS, DPC |  |  | NEW YORK | Y | 126000 | 1425 | 0 |  | 127425 | 63404.37 | 72500 | 0 | 0 | 0 | 72500 | 0 | 0 | 0 | 0 | 0 | 0.56896 | 0 | 0.56896 | 0 | 0.56896 | 0 | 63404.37 | 0 | 0 | 0 | 0 | 127425 | 0 | 0 | 0 | 127425 | 0 | 0 | 0 | 58781.34 | 126000 | 0 | 127425 | 0 | 0 | 2025-03-18
Grand Totals:

## Active
#VALUE!
Summary
#VALUE!
Count of Jobs: | 0
Job # | Contract | Customer | Project Manager | Estimator | Department | Closed Status | Base Contract | Approved Change Orders | (Work Done ) Outstanding Change Orders | Outstanding Allowance | Adjusted Contract Price | Estimated Total Direct Costs | QU Original Budget | CO Change Order Budget | Original GP | Change Order GP | Total Direct Budget | Over/Under Budget | Budgeted Gross Profit (Loss) | Estimated Gross Profit (Loss) | Estimated GP % | Current GP % | Prior Month1 GP | Variance Month1 GP | Prior Month2 GP | Variance Month2 GP | Prior Month3 GP | Variance Month3 GP | Direct Cost To Date | % Complete | Total Gross Profit Recognized To Date | Gross Profit Recognized Prior Years | Gross Profit (Loss) Recognized This Year | Total Amount Billed To Date | Remaining Billing Amount | Current Retainage Amount | Retainage % Held | Cash Received | Net Cash Flow | Costs and Estimated Earnings In Excess Of Billings | Billings In Excess Of Costs And Estimated Earnings | Prior Year Incurred Cost | Prior Year Billing | AR | AR Retainage | AP | AP Retainage | Last Projection Date
21-1009- | HT.224.130 HOLLAND TUNNEL / TULLY CONST. | Tully Construction Co., Inc. |  |  | NEW YORK | N | 2730505 | 196964.64 | 0 |  | 2906972 | 2322882 | 2243954.42 | 78928 | 0 | 0 | 2322882.42 | 0 | 0 | 0 | 0 | 0 | 0.79348 | 0 | 0.79348 | 0 | 0.79348 | 0 | 1626089.07 | 0 | 0 | 0 | 0 | 1679142.74 | 0 | 83957.15 | 0 | 1256708.31 | 0 | 0 | 0 | 1893.92 | 0 | 338477.28 | 1256708.31 | 10332.79 | 0 | 2025-03-18
21-1009- A | Holland Tunnel Extra Work / Slade Industries | Slade Industries, Inc. |  |  | NEW YORK | N | 22818.73 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1249.04 | 0 | 0 | 0 | 0 | 22818.73 | 0 | 0 | 0 | 22818.73 | 0 | 0 | 0 | 0 | 0 | 0 | 22818.73 | 0 | 0 | 2025-03-18
21-1021- | MA DOT #117036 - Interstate 90 Bridges - MIG CORP. | MIG CORPORATION, INC. |  |  | MASSACHUSETTS | N | 1200000 | 61306.28 | 0 |  | 1215635 | 1685651 | 1020000 | 28621.07 | 0 | 0 | 1048621.07 | 0 | 0 | 0 | 0 | 0 | 0.83138 | 0 | 0.83138 | 0 | 0.83138 | 0 | 1688209.37 | 0 | 0 | 0 | 0 | 1251681.28 | 0 | 0 | 0 | 1212741.02 | 0 | 0 | 0 | 1514692.75 | 1094760.26 | 38940.26 | 1212741.02 | 98783.5 | 0 | 2024-08-01
22-1004- | CT DOT 0040-0141 / HADDAM / AMER. BRDGE. | American Bridge Co. |  |  | CONNECTICUT | N | 3102105.09 | 718853.93 | 0 |  | 3711343 | 2968091.74 | 2288568 | 741524.5 | 0 | 0 | 3030092.5 | 0 | 0 | 0 | 0 | 0 | 0.79302 | 0 | 0.79644 | 0 | 0.80713 | 0 | 3519004.46 | 0 | 0 | 0 | 0 | 3765599.02 | 0 | 0 | 0 | 3341942.46 | 0 | 0 | 0 | 2481569.24 | 2471080 | 423656.56 | 3341942.46 | 232821.44 | 0 | 2024-08-05
22-1006- | CT DOT 165-509 / WINDSOR LOCKS / ROTHA | Rotha Contracting Co., Inc. |  |  | CONNECTICUT | N | 2228730 | 66000 | 0 |  | 2227040 | 2350000 | 1760000 | 0 | 0 | 0 | 1760000 | 0 | 0 | 0 | 0 | 0 | 0.76697 | 0 | 0.76697 | 0 | 0.76754 | 0 | 2263874.11 | 0 | 0 | 0 | 0 | 1786640.37 | 0 | 0 | 0 | 1712892.37 | 0 | 0 | 0 | 1352597.75 | 1230339.8 | 73748 | 1712892.37 | 97893.49 | 0 | 2024-08-07
22-1008- | CT DOT 170-3557 / MCNAMEE | McNamee Construction Corp. |  |  | CONNECTICUT | N | 1450000 | -149294.02 | 0 |  | 1096000 | 746280 | 987000 | -90720 | 0 | 0 | 896280 | 0 | 0 | 0 | 0 | 0 | 0.68907 | 0 | 0.68907 | 0 | 0.68907 | 0 | 644277.24 | 0 | 0 | 0 | 0 | 863555.98 | 0 | 0 | 0 | 861555.98 | 0 | 0 | 0 | 446657.61 | 681000 | 2000 | 861555.98 | 54206.91 | 0 | 2024-08-05
22-1009- | CT DOT 170-3551 / ROTHA | Rotha Contracting Co., Inc. |  |  | CONNECTICUT | N | 712300 | 0 | 0 |  | 712300 | 530000 | 530000 | 0 | 0 | 0 | 530000 | 0 | 0 | 0 | 0 | 0 | 0.74407 | 0 | 0.74407 | 0 | 0.74407 | 0 | 241053.47 | 0 | 0 | 0 | 0 | 353990 | 0 | 0 | 0 | 353990 | 0 | 0 | 0 | 59897.2 | 163000 | 0 | 353990 | 33744.73 | 0 | 2023-06-27
22-1010- | CT DOT 0171-0484 / BEAM END REPAIRS / MCNAMEE | McNamee Construction Corp. |  |  | CONNECTICUT | N | 1372941 | 132225.95 | 0 |  | 1409661 | 1005000 | 1005000 | 49160 | 0 | 0 | 1054160 | 0 | 0 | 0 | 0 | 0 | 0.70036 | 0 | 0.70036 | 0 | 0.70036 | 0 | 957003.1 | 0 | 0 | 0 | 0 | 1380347.55 | 0 | 0 | 0 | 1380347.55 | 0 | 0 | 0 | 280471.99 | 431370.1 | 0 | 1380347.55 | 19068.19 | 0 | 2023-06-27
23-1000- | NYC DOT HB1070QN / BREWER & CROSS BAY / COMMODORE | COMMODORE CONSTRUCTION CORP |  |  | NEW YORK | N | 2300000 | 0 | 0 |  | 2300000 | 1910000 | 1910000 | 0 | 0 | 0 | 1910000 | 0 | 0 | 0 | 0 | 0 | 0.83043 | 0 | 0.83043 | 0 | 0.83043 | 0 | 2156357.25 | 0 | 0 | 0 | 0 | 1330388.29 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 29605.87 | 25000 | 1210388.29 | 120000 | 264937.76 | 0 | 2025-03-13
23-1002- | MA DOT #122517 - TEWKSBURY - NEL CORP. | NEL Corp. |  |  | MASSACHUSETTS | N | 2416210 | 0 | 0 |  | 2416210 | 1720948 | 1720948 | 0 | 0 | 0 | 1720948 | 0 | 0 | 0 | 0 | 0 | 0.71225 | 0 | 0.71225 | 0 | 0.71225 | 0 | 14782.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5252.5 | 0 | 0 | 0 | 6895.2 | 0 | 2024-08-02
24-1001- | RK-19A / CMC / RFK BRIDGE PLATFORM | COMMODORE MAINTENANCE CORP |  |  | NEW YORK | N | 10000000 | 0 | 0 |  | 13700000 | 16943960 | 6621980 | 0 | 0 | 0 | 6621980 | 0 | 0 | 0 | 0 | 0 | 0.6622 | 0 | 0.6622 | 0 | 0.6622 | 0 | 3925411.39 | 0 | 0 | 0 | 0 | 5702625 | 0 | 0 | 0 | 4654000 | 0 | 0 | 0 | 0 | 0 | 1048625 | 4654000 | 113467.12 | 0 | 2025-03-13
24-1002- | NYC DDC / HWK1669A / JRCRUZ | JRCRUZ Corp. |  |  | NEW YORK | N | 617796 | 0 | 0 |  | 617796 | 94568 | 368315.2 | 0 | 0 | 0 | 368315.2 | 0 | 0 | 0 | 0 | 0 | 0.59618 | 0 | 0.59618 | 0 | 0.59618 | 0 | 94567.55 | 0 | 0 | 0 | 0 | 617796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617796 | 0 | 22379.35 | 0 | 2025-03-13
24-1003- | RI DOT 2024CB018 / AETNA BRIDGE / LAFAYETTE BRIDGE REPAIRS | Aetna Bridge Company |  |  | RHODE ISLAND | N | 513955.56 | 0 | 0 |  | 513955.56 | 300409.78 | 300409.78 | 0 | 0 | 0 | 300409.78 | 0 | 0 | 0 | 0 | 0 | 0.58451 | 0 | 0.58451 | 0 | 0.58451 | 0 | 54454.99 | 0 | 0 | 0 | 0 | 262966.58 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 212966.58 | 50000 | 15123.81 | 0 | 2025-03-13
24-1004- | Emergency Repairs / Willimantic | McNamee Construction Corp. |  |  | CONNECTICUT | N | 251517.42 | 0 | 0 |  | 251517.42 | 52830 | 183260 | 0 | 0 | 0 | 183260 | 0 | 0 | 0 | 0 | 0 | 0.72862 | 0 | 0 | 0 | 0 | 0 | 52829.68 | 0 | 0 | 0 | 0 | 150910.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150910.45 | 0 | 2554.68 | 0 | 2025-03-13
CT- - | CT Template |  |  |  | CONNECTICUT | N | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MA- - | MA Template |  |  |  | MASSACHUSETTS | N | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MO- - | MO Template |  |  |  | MISSOURI | N | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NJ- - | NJ Template |  |  |  | NEW JERSEY | N | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NY- - | NY Template |  |  |  | NEW YORK | N | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RI- - | RI Template |  |  |  | RHODE ISLAND | N | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Totals: