## Summary
#VALUE!
Active
For The Period Ended 2025-03-31
Count of Jobs: | 42
Job # | Contract | Customer | Project Manager | Estimator | Department | Closed Status | Base Contract | Approved Change Orders | (Work Done ) Outstanding Change Orders | Outstanding Allowance | Adjusted Contract Price | Estimated Total Direct Costs | QU Original Budget | CO Change Order Budget | Original GP | Change Order GP | Total Direct Budget | Over/Under Budget | Budgeted Gross Profit (Loss) | Estimated Gross Profit (Loss) | Estimated GP % | Current GP % | Prior Month1 GP | Variance Month1 GP | Prior Month2 GP | Variance Month2 GP | Prior Month3 GP | Variance Month3 GP | Direct Cost To Date | % Complete | Total Gross Profit Recognized To Date | Gross Profit Recognized Prior Years | Gross Profit (Loss) Recognized This Year | Total Amount Billed To Date | Remaining Billing Amount | Current Retainage Amount | Retainage % Held | Cash Received | Net Cash Flow | Costs and Estimated Earnings In Excess Of Billings | Billings In Excess Of Costs And Estimated Earnings | Prior Year Incurred Cost | Prior Year Billing | AR | AR Retainage | AP | AP Retainage | Last Projection Date
21-1001- | CT DOT 108-0186 McNamee Construction Corp. | McNamee Construction Corp. |  |  | CONNECTICUT | Y | 1386800 | 138412.82 | 0 |  | 1525212.82 | 1092176 | 1097168 | 93510.05 | 289632 | 44902.77 | 1190678.05 | 98502.05 | 334534.77 | 433036.82 | 0.21934 | 0.28392 | 0.78066 | -0.49674 | 0.78066 | -0.49674 | 0.78066 | -0.49674 | 1092176 | 1 | 433036.82 |  | 433036.82 | 1525212.82 | 0 | 0 | 0 | 1525212.82 | 433036.82 | 0 | 0 | 0 | 0 | 0 | 1525212.82 | 0 | 0 | 2023-09-06
21-1002- | CT DOT 51-272-R1 McNamee Construction Corp | McNamee Construction Corp. |  |  | CONNECTICUT | Y | 667388.43 | 1960164.17 | 15911.4 |  | 2643464 | 1699645 | 546640 | 1153005 | 120748.43 | 807159.17 | 1699645 | 0 | 943819 | 943819 | 0.35704 | 0.35704 | 0.64685 | -0.28982 | 0.64685 | -0.28982 | 0.64685 | -0.28982 | 1168147.67 | 0.68729 | 648676.6153 |  | 648676.6153 | 2627552.6 | 15911.4 | 0 | 0 | 2627552.6 | 1459404.93 | 0 | 810728.3147 | 297217.35 | 1087091.96 | 0 | 2627552.6 | 7661.39 | 0 | 2024-08-07
21-1003- | CT DOT 163-196 McNamee Construction Corp | McNamee Construction Corp. |  |  | CONNECTICUT | Y | 1095500 | 1586695.79 | 0 |  | 2682195.79 | 2066263.1 | 876400 | 847362.26 | 219100 | 739333.53 | 1723762.26 | -342500.84 | 958433.53 | 615932.69 | 0.35733 | 0.22964 | 0.64267 | -0.41303 | 0.64267 | -0.41303 | 0.64267 | -0.41303 | 2065962.78 | 0.99985 | 615843.1676 |  | 615843.1676 | 2682195.79 | 0 | 0 | 0 | 2682195.79 | 616233.01 | 0 | 389.8424 | 241.86 | 0 | 0 | 2682195.79 | 240289.36 | 0 | 2025-03-18
21-1004- | CT COT 78-092 McNamee Construction Corp | McNamee Construction Corp. |  |  | CONNECTICUT | Y | 270080 | 0 | 0 |  | 270080 | 229213.54 | 216670.4 | 0 | 53409.6 | 0 | 216670.4 | -12543.14 | 53409.6 | 40866.46 | 0.19775 | 0.15131 | 0.80224 | -0.65093 | 0.80224 | -0.65093 | 0.80224 | -0.65093 | 229213.54 | 1 | 40866.46 |  | 40866.46 | 270080 | 0 | 0 | 0 | 270080 | 40866.46 | 0 | 0 | 0 | 0 | 0 | 270080 | 0 | 0 | 2023-09-06
21-1005- | CT DOT 63-719 Rotha Contracting Co., Inc. | Rotha Contracting Co., Inc. |  |  | CONNECTICUT | Y | 920079 | 22237.44 | -5.457e-11 |  | 942316.44 | 692639.17 | 736063.2 | 0 | 184015.8 | 22237.44 | 736063.2 | 43424.03 | 206253.24 | 249677.27 | 0.21888 | 0.26496 | 0.78112 | -0.51616 | 0.78112 | -0.51616 | 0.78112 | -0.51616 | 692639.17 | 1 | 249677.27 |  | 249677.27 | 942316.44 | 0 | 0 | 0 | 942316.44 | 249677.27 | 0 | 0 | 0 | 0 | 0 | 942316.44 | 6889.54 | 0 | 2025-03-18
21-1006- | CT DOT 42-0325 New England Infrastructure, Inc. | New England Infrastructure, Inc. |  |  | CONNECTICUT | Y | 83725 | 0 | 0 |  | 83725 | 61242.88 | 0 | 0 | 83725 | 0 | 0 | -61242.88 | 83725 | 22482.12 | 1 | 0.26852 | 0 | 0.26852 | 0 | 0.26852 | 0 | 0.26852 | 61242.88 | 1 | 22482.12 |  | 22482.12 | 83725 | 0 | 0 | 0 | 83725 | 22482.12 | 0 | 0 | 0 | 0 | 0 | 83725 | 0 | 0 | 2024-03-05
21-1007- | CT DOT 146-199 Town of Vernon | Town of Vernon |  |  | CONNECTICUT | Y | 150000 | 20300 | 0 |  | 170300 | 74344.1 | 0 | 15100 | 150000 | 5200 | 15100 | -59244.1 | 155200 | 95955.9 | 0.91133 | 0.56345 | 0.088667 | 0.47479 | 0.088667 | 0.47479 | 0.088667 | 0.47479 | 74344.1 | 1 | 95955.9 |  | 95955.9 | 170300 | 0 | 0 | 0 | 170300 | 95955.9 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 0 | 2025-03-18
21-1008- | CT DOT 83-267 Mohawk Northeast, Inc. | Mohawk Northeast, Inc. |  |  | CONNECTICUT | Y | 418500 | -13050 | 0 |  | 405450 | 197359.43 | 334800 | -135538 | 83700 | 122488 | 199262 | 1902.57 | 206188 | 208090.57 | 0.50854 | 0.51323 | 0.49146 | 0.021776 | 0.49146 | 0.021776 | 0.49146 | 0.021776 | 197359.43 | 1 | 208090.57 |  | 208090.57 | 405450 | 0 | 0 | 0 | 405450 | 208090.57 | 0 | 0 | 0 | 4860 | 0 | 405450 | 0 | 0 | 2025-03-18
21-1009- | HT.224.130 HOLLAND TUNNEL / TULLY CONST. | Tully Construction Co., Inc. |  |  | NEW YORK | N | 2730505 | 196964.64 | -1248326.64 |  | 1679143 | 1627144.05 | 2243954.42 | 78928 | 486550.58 | 118036.64 | 2322882.42 | 695738.37 | -643739.42 | 51998.95 | -0.38337 | 0.030968 | 0.79348 | -0.76251 | 0.79348 | -0.76251 | 0.79348 | -0.76251 | 1627143.41 | 1 | 51998.9295 |  | 51998.9295 | 1679142.74 | 0.26 | 83957.15 | 0.05 | 1579603.6 | -47539.81 | 0 | 0.40045 | 1103808.57 | 901423.78 | 15581.99 | 1579603.6 | 186.24 | 0 | 2025-03-18
21-1009- A | Holland Tunnel Extra Work / Slade Industries | Slade Industries, Inc. |  |  | NEW YORK | Y | 22818.73 | 0 | 0 |  | 22818.73 | 0 | 0 | 0 | 22818.73 | 0 | 0 | 0 | 22818.73 | 22818.73 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1249.04 | 0 | 0 |  | 0 | 22818.73 | 0 | 0 | 0 | 22818.73 | 21569.69 | 0 | 21569.69 | 1249.04 | 0 | 0 | 22818.73 | 0 | 0 | 2025-03-18
21-1010- | NY Valhalla Boiler Tank | Vahalla Tank |  |  | NEW YORK | Y | 52500 | 12400 | 0 |  | 64900 | 22247 | 0 | 0 | 52500 | 12400 | 0 | -22247 | 64900 | 42653 | 1 | 0.65721 | 0 | 0.65721 | 0 | 0.65721 | 0 | 0.65721 | 22247 | 1 | 42653 |  | 42653 | 64900 | 0 | 0 | 0 | 64900 | 42653 | 0 | 0 | 0 | 0 | 0 | 64900 | 0 | 0 | 2023-09-06
21-1011- | NYS DOT #D264563 - HEMPSTEAD - H&L CONT. | H & L Contracting, LLC |  |  | NEW YORK | Y | 478000 | -91775.53 | -0.47 |  | 386224 | 705323.58 | 346500 | 0 | 131500 | -91775.53 | 346500 | -358823.58 | 39724 | -319099.58 | 0.10285 | -0.8262 | 0.89715 | -1.7233 | 0.89715 | -1.7233 | 0.89715 | -1.7233 | 705323.58 | 1 | -319099.58 |  | -319099.58 | 386224.47 | -0.47 | 0 | 0 | 386224.47 | -319099.11 | 0 | 0.47 | 167358.31 | 128996.9 | 0 | 386224.47 | 44490.23 | 0 | 2025-03-18
21-1013- | CT DOT 0096-0200 Waters Construction Co. | Waters Construction Co. |  |  | CONNECTICUT | Y | 244225.34 | 0 | 0 |  | 244225.34 | 0 | 0 | 0 | 244225.34 | 0 | 0 | 0 | 244225.34 | 244225.34 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 |  | 0 | 244225.34 | 0 | 0 | 0 | 244225.34 | 244225.34 | 0 | 244225.34 | 0 | 0 | 0 | 244225.34 | 0 | 0
21-1014- | NR-42 Gas Holder NYC 2017-4 Welkin Construction | Welkin Mechanical, LLC |  |  | NEW YORK | Y | 12019 | 0 | 0 |  | 12019 | 0 | 0 | 0 | 12019 | 0 | 0 | 0 | 12019 | 12019 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 |  | 0 | 12018.98 | 0.02 | 0 | 0 | 12018.98 | 12018.98 | 0 | 12018.98 | 0 | 0 | 0 | 12018.98 | 0 | 0
21-1015- | CT DOT 63-0654 Mohawn Northeast, Inc. | Mohawk Northeast, Inc. |  |  | CONNECTICUT | Y | 425000 | 0 | 0 |  | 425000 | 321840.71 | 0 | 0 | 425000 | 0 | 0 | -321840.71 | 425000 | 103159.29 | 1 | 0.24273 | 0 | 0.24273 | 0 | 0.24273 | 0 | 0.24273 | 321840.71 | 1 | 103159.29 |  | 103159.29 | 425000 | 0 | 0 | 0 | 425000 | 103159.29 | 0 | 0 | 0 | 0 | 0 | 425000 | 0 | 0 | 2023-09-06
21-1016- | Missouri Substation Painting Fort Kickapoo Substation |  |  |  | MISSOURI | Y | 91980 | 9500 | 0 |  | 101480 | 48804.98 | 0 | 0 | 91980 | 9500 | 0 | -48804.98 | 101480 | 52675.02 | 1 | 0.51907 | 0 | 0.51907 | 0 | 0.51907 | 0 | 0.51907 | 48804.98 | 1 | 52675.02 |  | 52675.02 | 101480 | 0 | 0 | 0 | 101480 | 52675.02 | 0 | 0 | 0 | 0 | 0 | 101480 | 0 | 0 | 2021-12-31
21-1017- | CT DOT 0154-0125 - ARBORIO CORP | ARBORIO COROPORATION |  |  | CONNECTICUT | Y | 352000 | 33812.04 | 0 |  | 385812.04 | 219653.46 | 287820 | 24384.98 | 64180 | 9427.06 | 312204.98 | 92551.52 | 73607.06 | 166158.58 | 0.19078 | 0.43067 | 0.80922 | -0.37854 | 0.80922 | -0.37854 | 0.80922 | -0.37854 | 219653.46 | 1 | 166158.58 |  | 166158.58 | 385812.04 | 0 | 0 | 0 | 385812.04 | 166158.58 | 0 | 0 | 0 | 0 | 0 | 385812.04 | 10458.67 | 0 | 2023-09-06
21-1018- | HUNT'S POINT - DEAN ENERGY SOLUTIONS | DEAN ENERGY SOLUTIONS |  |  | NEW YORK | Y | 30000 | 0 | 0 |  | 30000 | 15209.84 | 21000 | 0 | 9000 | 0 | 21000 | 5790.16 | 9000 | 14790.16 | 0.3 | 0.49301 | 0.7 | -0.20699 | 0.7 | -0.20699 | 0.7 | -0.20699 | 15209.84 | 1 | 14790.16 |  | 14790.16 | 30000 | 0 | 0 | 0 | 30000 | 14790.16 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 2023-12-07
21-1019- | SIGNATURE BRIDGE NJDOT - CMC | COMMODORE MAINTENANCE CORP |  |  | NEW JERSEY | Y | 5100000 | 930000 | 0 |  | 6030000 | 4374347.6 | 4743000 | 0 | 357000 | 930000 | 4743000 | 368652.4 | 1287000 | 1655652.4 | 0.21343 | 0.27457 | 0.78657 | -0.512 | 0.78657 | -0.512 | 0.78657 | -0.512 | 4371438.65 | 0.99933 | 1654551.3878 |  | 1654551.3878 | 6030000 | 0 | 0 | 0 | 6030000 | 1658561.35 | 0 | 4009.9622 | 10918.24 | 130000 | 0 | 6030000 | 283687.42 | 0 | 2025-03-18
21-1020- | NY 17-530 REHAB VARIOUS BRIDGES WESTCHESTER - LAURA | LAURA LI INDUSTRIES |  |  | NEW YORK | Y | 133850 | 400 | 0 |  | 134250 | 21695.28 | 100850 | 0 | 33000 | 400 | 100850 | 79154.72 | 33400 | 112554.72 | 0.24879 | 0.8384 | 0.75121 | 0.087186 | 0.75121 | 0.087186 | 0.75121 | 0.087186 | 21695.28 | 1 | 112554.72 |  | 112554.72 | 134250 | 0 | 0 | 0 | 134250 | 112554.72 | 0 | 0 | 0 | 0 | 0 | 134250 | 0 | 0 | 2023-12-07
21-1021- | MA DOT #117036 - Interstate 90 Bridges - MIG CORP. | MIG CORPORATION, INC. |  |  | MASSACHUSETTS | N | 1200000 | 45671.02 | 0 |  | 1245671.02 | 1688209.91 | 1020000 | 28621.07 | 180000 | 17049.95 | 1048621.07 | -639588.84 | 197049.95 | -442538.89 | 0.15819 | -0.35526 | 0.84181 | -1.1971 | 0.83138 | -1.1866 | 0.83138 | -1.1866 | 1688209.37 | 1 | -442538.7484 |  | -442538.7484 | 1245671.02 | 0 | 0 | 0 | 1245671.02 | -442538.35 | 0 | 0.39845 | 59148.28 | 45671.02 | 0 | 1245671.02 | 94145.76 | 0 | 2024-12-31
22-1001- | CRANES AT HOLTSVILLE GT - NATIONAL GRID | National Grid |  |  | NEW YORK | Y | 141400 | -8000 | 0 |  | 133400 | 201907.89 | 120190 | 0 | 21210 | -8000 | 120190 | -81717.89 | 13210 | -68507.89 | 0.099025 | -0.51355 | 0.90097 | -1.4145 | 0.90097 | -1.4145 | 0.90097 | -1.4145 | 201907.89 | 1 | -68507.89 |  | -68507.89 | 133400 | 0 | 0 | 0 | 133400 | -68507.89 | 0 | 0 | 0 | 0 | 0 | 133400 | 6300.34 | 0 | 2023-09-06
22-1002- | H-STREET BRIDGE REHABILITATION - MCNAMEE - PV | McNamee Construction Corp. |  |  | NEW YORK | Y | 51625 | 0 | -1475 |  | 50150 | 19522.76 | 43300 | 0 | 8325 | 0 | 43300 | 23777.24 | 6850 | 30627.24 | 0.13659 | 0.61071 | 0.83874 | -0.22803 | 0.83874 | -0.22803 | 0.83874 | -0.22803 | 19522.76 | 1 | 30627.24 |  | 30627.24 | 50150 | 0 | 0 | 0 | 50150 | 30627.24 | 0 | 0 | 0 | 0 | 0 | 50150 | 0 | 0 | 2025-03-18
22-1003- | MOUNT OLIVE, NJ - LEAD PAINT REMOVAL ON WATER TANK - EBI | EBI Consulting |  |  | NEW JERSEY | Y | 32600 | 0 | 0 |  | 32600 | 8332.41 | 28468 | 0 | 4132 | 0 | 28468 | 20135.59 | 4132 | 24267.59 | 0.12675 | 0.7444 | 0.87325 | -0.12885 | 0.87325 | -0.12885 | 0.87325 | -0.12885 | 7950.47 | 0.95416 | 23155.2151 |  | 23155.2151 | 32600 | 0 | 0 | 0 | 32600 | 24649.53 | 0 | 1494.3149 | 0 | 0 | 0 | 32600 | 0 | 0 | 2023-12-07
22-1004- | CT DOT 0040-0141 / HADDAM / AMER. BRDGE. | American Bridge Co. |  |  | CONNECTICUT | N | 3102105.09 | 718853.93 | -262482.02 |  | 3558477 | 3519005 | 2288568 | 741524.5 | 813537.09 | -22670.57 | 3030092.5 | -488912.5 | 528384.5 | 39472 | 0.14849 | 0.011092 | 0.79302 | -0.78193 | 0.79302 | -0.78193 | 0.79302 | -0.78193 | 3520412.13 | 1.0004 | 39487.7835 |  | 39487.7835 | 3765599.02 | -207122.02 | 0 | 0 | 3411940.84 | -108471.29 | 0 | 205699.1065 | 905314.35 | 856319.02 | 353658.18 | 3411940.84 | 206943.06 | 0 | 2024-12-31
22-1005- | RI DOT / #2022CB046 / AETNA BRIDGE CO. | Aetna Bridge Company |  |  | RHODE ISLAND | Y | 855500 | 0 | 0 |  | 855500 | 489122.54 | 641250 | 0 | 214250 | 0 | 641250 | 152127.46 | 214250 | 366377.46 | 0.25044 | 0.42826 | 0.74956 | -0.3213 | 0.74956 | -0.3213 | 0.74956 | -0.3213 | 489122.54 | 1 | 366377.46 |  | 366377.46 | 855500 | 0 | 0 | 0 | 855500 | 366377.46 | 0 | 0 | 14380.08 | 27862.5 | 0 | 855500 | 19110.03 | 0 | 2025-03-18
22-1006- | CT DOT 165-509 / WINDSOR LOCKS / ROTHA | Rotha Contracting Co., Inc. |  |  | CONNECTICUT | N | 2228730 | 66000 | -508089.63 |  | 1786640.37 | 2264015 | 1760000 | 0 | 468730 | 66000 | 1760000 | -504015 | 26640.37 | -477374.63 | 0.014911 | -0.26719 | 0.76697 | -1.0342 | 0.76697 | -1.0342 | 0.76697 | -1.0342 | 2264014.11 | 1 | -477374.4423 |  | -477374.4423 | 1786640.37 | 0 | 0 | 0 | 1786640.37 | -477373.74 | 0 | 0.70234 | 907599.82 | 556300.57 | 0 | 1786640.37 | 72099.84 | 0 | 2024-12-31
22-1007- | RFK BRIDGE / COMMODORE MAINT. | COMMODORE MAINTENANCE CORP |  |  | NEW YORK | Y | 1850000 | 0 | 0 |  | 1850000 | 1678795.86 | 1354000 | 0 | 496000 | 0 | 1354000 | -324795.86 | 496000 | 171204.14 | 0.26811 | 0.092543 | 0.73189 | -0.63935 | 0.73189 | -0.63935 | 0.73189 | -0.63935 | 1678795.86 | 1 | 171204.14 |  | 171204.14 | 1850000 | 0 | 0 | 0 | 1850000 | 171204.14 | 0 | 0 | 0 | 0 | 0 | 1850000 | 72155.75 | 0 | 2025-03-18
22-1008- | CT DOT 170-3557 / MCNAMEE | McNamee Construction Corp. |  |  | CONNECTICUT | N | 1450000 | -149294.02 | -204705.98 |  | 1096000 | 746280 | 987000 | -90720 | 463000 | -58574.02 | 896280 | 150000 | 199720 | 349720 | 0.18223 | 0.31909 | 0.68907 | -0.36998 | 0.68907 | -0.36998 | 0.68907 | -0.36998 | 644620.89 | 0.86378 | 302080.744 |  | 302080.744 | 896055.98 | 199944.02 | 0 | 0 | 861555.98 | 216935.09 | 50645.654 | 0 | 192848.27 | 182555.98 | 34500 | 861555.98 | 5805.93 | 0 | 2024-08-05
22-1009- | CT DOT 170-3551 / ROTHA | Rotha Contracting Co., Inc. |  |  | CONNECTICUT | N | 712300 | 0 | 0 |  | 712300 | 530000 | 530000 | 0 | 182300 | 0 | 530000 | 0 | 182300 | 182300 | 0.25593 | 0.25593 | 0.74407 | -0.48814 | 0.74407 | -0.48814 | 0.74407 | -0.48814 | 241600.33 | 0.45585 | 83101.3965 |  | 83101.3965 | 389990 | 322310 | 0 | 0 | 389990 | 148389.67 | 0 | 65288.2735 | 160876.8 | 190990 | 0 | 389990 | 10209.83 | 0 | 2023-06-27
22-1010- | CT DOT 0171-0484 / BEAM END REPAIRS / MCNAMEE | McNamee Construction Corp. |  |  | CONNECTICUT | N | 1408029.65 | 132225.95 | -130594.6 |  | 1409661 | 1005000 | 1005000 | 49160 | 403029.65 | 83065.95 | 1054160 | 49160 | 355501 | 404661 | 0.25219 | 0.28706 | 0.68441 | -0.39734 | 0.68441 | -0.39734 | 0.68441 | -0.39734 | 966987.34 | 0.96218 | 389355.2876 |  | 389355.2876 | 1419311.2 | -9650.2 | 0 | 0 | 1380347.55 | 413360.21 | 0 | 62968.5724 | 628830.78 | 948977.45 | 38963.65 | 1380347.55 | 10139.68 | 0 | 2023-06-27
22-1095- | BRIDGE PAINTING OF SEVEN BRIDGES - CMC - PETER | COMMODORE MAINTENANCE CORP |  |  | NEW YORK | Y | 288000 | 0 | 0 |  | 288000 | 421130.4 | 240000 | 0 | 48000 | 0 | 240000 | -181130.4 | 48000 | -133130.4 | 0.16667 | -0.46226 | 0.83333 | -1.2956 | 0.83333 | -1.2956 | 0.83333 | -1.2956 | 421130.4 | 1 | -133130.4 |  | -133130.4 | 288000 | 0 | 0 | 0 | 288000 | -133130.4 | 0 | 0 | 0 | 0 | 0 | 288000 | 0 | 0 | 2025-03-18
23-1000- | NYC DOT HB1070QN / BREWER & CROSS BAY / COMMODORE | COMMODORE CONSTRUCTION CORP |  |  | NEW YORK | N | 2300000 | 0 | 0 |  | 2300000 | 2186175 | 1910000 | 0 | 390000 | 0 | 1910000 | -276175 | 390000 | 113825 | 0.16957 | 0.049489 | 0.83043 | -0.78094 | 0.83043 | -0.78094 | 0.83043 | -0.78094 | 2186267.51 | 1 | 113829.8166 |  | 113829.8166 | 1546448.32 | 753551.68 | 0 | 0 | 442000 | -1744267.51 | 753649.0066 | 0 | 1419528.04 | 1305388.29 | 1104448.32 | 442000 | 226809.48 | 0 | 2025-03-13
23-1001- | NYPA COOLING TOWER / MACAN DEVE | MACAN DEVE ENGINEERS, DPC |  |  | NEW YORK | Y | 126000 | 1425 | 0 |  | 127425 | 63404.37 | 72500 | 0 | 53500 | 1425 | 72500 | 9095.63 | 54925 | 64020.63 | 0.43104 | 0.50242 | 0.56896 | -0.066544 | 0.56896 | -0.066544 | 0.56896 | -0.066544 | 63404.37 | 1 | 64020.63 |  | 64020.63 | 127425 | 0 | 0 | 0 | 127425 | 64020.63 | 0 | 0 | 4623.03 | 1425 | 0 | 127425 | 0 | 0 | 2025-03-18
23-1002- | MA DOT #122517 - TEWKSBURY - NEL CORP. | NEL Corp. |  |  | MASSACHUSETTS | N | 2416210 | 0 | 0 |  | 2416210 | 1720948 | 1720948 | 0 | 695262 | 0 | 1720948 | 0 | 695262 | 695262 | 0.28775 | 0.28775 | 0.71225 | -0.4245 | 0.71225 | -0.4245 | 0.71225 | -0.4245 | 44375.77 | 0.025786 | 17927.7855 |  | 17927.7855 | 0 | 2416210 | 0 | 0 | 0 | -44375.77 | 62303.5555 | 0 | 6895.2 | 0 | 0 | 0 | 5135 | 0 | 2024-08-02
24-1001- | RK-19A / CMC / RFK BRIDGE PLATFORM | COMMODORE MAINTENANCE CORP |  |  | NEW YORK | N | 13700000 | -3700000 | 0 |  | 10000000 | 6621980 | 6621980 | 0 | 7078020 | -3700000 | 6621980 | 0 | 3378020 | 3378020 | 0.3378 | 0.3378 | 0.6622 | -0.3244 | 0.6622 | -0.3244 | 0.6622 | -0.3244 | 3925459.68 | 0.59279 | 2002464.7172 |  | 2002464.7172 | 6078005 | 3921995 | 0 | 0 | 5799000 | 1873540.32 | 0 | 150080.6028 | 3517103.89 | 5702625 | 279005 | 5799000 | 90363.41 | 0 | 2025-03-25
24-1002- | NYC DDC / HWK1669A / JRCRUZ | JRCRUZ Corp. |  |  | NEW YORK | N | 617796 | 0 | 0 |  | 617796 | 94567.41 | 368315.2 | 0 | 249480.8 | 0 | 368315.2 | 273747.79 | 249480.8 | 523228.59 | 0.40382 | 0.84693 | 0.59618 | 0.25075 | 0.59618 | 0.25075 | 0.59618 | 0.25075 | 94567.55 | 1 | 523229.3646 |  | 523229.3646 | 617796 | 0 | 0 | 0 | 533516.39 | 438948.84 | 0.9146 | 0 | 90229.19 | 617796 | 84279.61 | 533516.39 | 18018.21 | 0 | 2025-03-13
24-1003- | RI DOT 2024CB018 / AETNA BRIDGE / LAFAYETTE BRIDGE REPAIRS | Aetna Bridge Company |  |  | RHODE ISLAND | N | 513955.56 | 0 | 0 |  | 513955.56 | 300409.78 | 300409.78 | 0 | 213545.78 | 0 | 300409.78 | 0 | 213545.78 | 213545.78 | 0.41549 | 0.41549 | 0.58451 | -0.16901 | 0.58451 | -0.16901 | 0.58451 | -0.16901 | 54454.99 | 0.18127 | 38709.2368 |  | 38709.2368 | 262966.58 | 250988.98 | 0 | 0 | 252318.34 | 197863.35 | 0 | 169802.3532 | 54439.79 | 262966.58 | 10648.24 | 252318.34 | 3917.92 | 0 | 2025-03-13
24-1004- | Emergency Repairs / Willimantic | McNamee Construction Corp. |  |  | CONNECTICUT | N | 251517.42 | 0 | -161517.42 |  | 90000 | 52830.48 | 183260 | 0 | 68257.42 | 0 | 183260 | 130429.52 | -93260 | 37169.52 | -1.0362 | 0.41299 | 0.72862 | -0.31562 | 0.72862 | -0.31562 | 0.72862 | -0.31562 | 52829.68 | 0.99998 | 37168.9572 |  | 37168.9572 | 150910.45 | -60910.45 | 0 | 0 | 0 | -52829.68 | 0 | 60911.8128 | 48215.13 | 150910.45 | 150910.45 | 0 | 5698.73 | 0 | 2025-03-13
24-1005- | CT DOT 0015-0339 / BRIDGE #02475 / BRIDGEPORT / MOHAWK | Mohawk Northeast, Inc. |  |  | CONNECTICUT | N | 3985840 | 0 | 0 |  | 3985840 | 3149649 | 3149649 | 0 | 836191 | 0 | 3149649 | 0 | 836191 | 836191 | 0.20979 | 0.20979 | 0.79021 | -0.58042 | 0.79021 | -0.58042 | 0.79021 | -0.58042 | 6570.14 | 0.002086 | 1744.287 |  | 1744.287 | 159434 | 3826406 | 0 | 0 | 159434 | 152863.86 | 0 | 151119.573 | 0 | 0 | 0 | 159434 | 6410 | 0 | 2025-02-01
25-1000- | CT DOT 0053-0196 / ROUTE 2, GLASTONBURY / MCNAMEE | McNamee Construction Corp. |  |  | CONNECTICUT | N | 2105000 | 0 | 0 |  | 2105000 | 1679195 | 1679195 | 0 | 425805 | 0 | 1679195 | 0 | 425805 | 425805 | 0.20228 | 0.20228 | 0.79772 | -0.59543 | 0.79772 | -0.59543 | 0 | 0.20228 | 2500 | 0.0014888 | 633.9422 |  | 633.9422 | 84200 | 2020800 | 0 | 0 | 0 | -2500 | 0 | 81066.0578 | 0 | 0 | 84200 | 0 | 2500 | 0 | 2025-02-01
25-1001- | CT DOT CHURCH ST / MCNAMEE | McNamee Construction Corp. |  |  | CONNECTICUT | N | 177500 | 0 | -177500 |  | 0 | 0 | 138963.62 | 0 | 38536.38 | 0 | 138963.62 | 138963.62 | -138963.62 | 0 | 0 | 0 | 0.78289 | -0.78289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 7100 | -7100 | 0 | 0 | 0 | 0 | 0 | 7100 | 0 | 0 | 7100 | 0 | 0 | 0
Grand Totals:
[9 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Department Totals: | Department | Costs and Estimated Earnings In Excess Of Billings
[6 empty] | CONNECTICUT | SUM from above
[6 empty] | MASSACHUSETTS | SUM from above
[6 empty] | NEW YORK | SUM from above
[6 empty] | RHODE ISLAND | SUM from above

## Completed Contracts
#VALUE!
Active
For The Period Ended 2025-03-31
Count of Jobs: | 18
Job # | Contract | Customer | Project Manager | Estimator | Department | Closed Status | Base Contract | Approved Change Orders | (Work Done ) Outstanding Change Orders | Outstanding Allowance | Adjusted Contract Price | Estimated Total Direct Costs | QU Original Budget | CO Change Order Budget | Original GP | Change Order GP | Total Direct Budget | Over/Under Budget | Budgeted Gross Profit (Loss) | Estimated Gross Profit (Loss) | Estimated GP % | Current GP % | Prior Month1 GP | Variance Month1 GP | Prior Month2 GP | Variance Month2 GP | Prior Month3 GP | Variance Month3 GP | Direct Cost To Date | % Complete | Total Gross Profit Recognized To Date | Gross Profit Recognized Prior Years | Gross Profit (Loss) Recognized This Year | Total Amount Billed To Date | Remaining Billing Amount | Current Retainage Amount | Retainage % Held | Cash Received | Net Cash Flow | Costs and Estimated Earnings In Excess Of Billings | Billings In Excess Of Costs And Estimated Earnings | Prior Year Incurred Cost | Prior Year Billing | AR | AR Retainage | AP | AP Retainage | Last Projection Date
21-1001- | CT DOT 108-0186 McNamee Construction Corp. | McNamee Construction Corp. |  |  | CONNECTICUT | Y | 1386800 | 138412.82 | 0 |  | 1525212.82 | 1092176 | 1097168 | 93510.05 | 289632 | 44902.77 | 1190678.05 | 98502.05 | 334534.77 | 433036.82 | 0.21934 | 0.28392 | 0.78066 | -0.49674 | 0.78066 | -0.49674 | 0.78066 | -0.49674 | 1092176 | 1 | 433036.82 |  | 433036.82 | 1525212.82 | 0 | 0 | 0 | 1525212.82 | 433036.82 | 0 | 0 | 0 | 0 | 0 | 1525212.82 | 0 | 0 | 2023-09-06
21-1004- | CT COT 78-092 McNamee Construction Corp | McNamee Construction Corp. |  |  | CONNECTICUT | Y | 270080 | 0 | 0 |  | 270080 | 229213.54 | 216670.4 | 0 | 53409.6 | 0 | 216670.4 | -12543.14 | 53409.6 | 40866.46 | 0.19775 | 0.15131 | 0.80224 | -0.65093 | 0.80224 | -0.65093 | 0.80224 | -0.65093 | 229213.54 | 1 | 40866.46 |  | 40866.46 | 270080 | 0 | 0 | 0 | 270080 | 40866.46 | 0 | 0 | 0 | 0 | 0 | 270080 | 0 | 0 | 2023-09-06
21-1005- | CT DOT 63-719 Rotha Contracting Co., Inc. | Rotha Contracting Co., Inc. |  |  | CONNECTICUT | Y | 920079 | 22237.44 | -5.457e-11 |  | 942316.44 | 692639.17 | 736063.2 | 0 | 184015.8 | 22237.44 | 736063.2 | 43424.03 | 206253.24 | 249677.27 | 0.21888 | 0.26496 | 0.78112 | -0.51616 | 0.78112 | -0.51616 | 0.78112 | -0.51616 | 692639.17 | 1 | 249677.27 |  | 249677.27 | 942316.44 | 0 | 0 | 0 | 942316.44 | 249677.27 | 0 | 0 | 0 | 0 | 0 | 942316.44 | 6889.54 | 0 | 2025-03-18
21-1006- | CT DOT 42-0325 New England Infrastructure, Inc. | New England Infrastructure, Inc. |  |  | CONNECTICUT | Y | 83725 | 0 | 0 |  | 83725 | 61242.88 | 0 | 0 | 83725 | 0 | 0 | -61242.88 | 83725 | 22482.12 | 1 | 0.26852 | 0 | 0.26852 | 0 | 0.26852 | 0 | 0.26852 | 61242.88 | 1 | 22482.12 |  | 22482.12 | 83725 | 0 | 0 | 0 | 83725 | 22482.12 | 0 | 0 | 0 | 0 | 0 | 83725 | 0 | 0 | 2024-03-05
21-1007- | CT DOT 146-199 Town of Vernon | Town of Vernon |  |  | CONNECTICUT | Y | 150000 | 20300 | 0 |  | 170300 | 74344.1 | 0 | 15100 | 150000 | 5200 | 15100 | -59244.1 | 155200 | 95955.9 | 0.91133 | 0.56345 | 0.088667 | 0.47479 | 0.088667 | 0.47479 | 0.088667 | 0.47479 | 74344.1 | 1 | 95955.9 |  | 95955.9 | 170300 | 0 | 0 | 0 | 170300 | 95955.9 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 0 | 2025-03-18
21-1008- | CT DOT 83-267 Mohawk Northeast, Inc. | Mohawk Northeast, Inc. |  |  | CONNECTICUT | Y | 418500 | -13050 | 0 |  | 405450 | 197359.43 | 334800 | -135538 | 83700 | 122488 | 199262 | 1902.57 | 206188 | 208090.57 | 0.50854 | 0.51323 | 0.49146 | 0.021776 | 0.49146 | 0.021776 | 0.49146 | 0.021776 | 197359.43 | 1 | 208090.57 |  | 208090.57 | 405450 | 0 | 0 | 0 | 405450 | 208090.57 | 0 | 0 | 0 | 4860 | 0 | 405450 | 0 | 0 | 2025-03-18
21-1010- | NY Valhalla Boiler Tank | Vahalla Tank |  |  | NEW YORK | Y | 52500 | 12400 | 0 |  | 64900 | 22247 | 0 | 0 | 52500 | 12400 | 0 | -22247 | 64900 | 42653 | 1 | 0.65721 | 0 | 0.65721 | 0 | 0.65721 | 0 | 0.65721 | 22247 | 1 | 42653 |  | 42653 | 64900 | 0 | 0 | 0 | 64900 | 42653 | 0 | 0 | 0 | 0 | 0 | 64900 | 0 | 0 | 2023-09-06
21-1015- | CT DOT 63-0654 Mohawn Northeast, Inc. | Mohawk Northeast, Inc. |  |  | CONNECTICUT | Y | 425000 | 0 | 0 |  | 425000 | 321840.71 | 0 | 0 | 425000 | 0 | 0 | -321840.71 | 425000 | 103159.29 | 1 | 0.24273 | 0 | 0.24273 | 0 | 0.24273 | 0 | 0.24273 | 321840.71 | 1 | 103159.29 |  | 103159.29 | 425000 | 0 | 0 | 0 | 425000 | 103159.29 | 0 | 0 | 0 | 0 | 0 | 425000 | 0 | 0 | 2023-09-06
21-1016- | Missouri Substation Painting Fort Kickapoo Substation |  |  |  | MISSOURI | Y | 91980 | 9500 | 0 |  | 101480 | 48804.98 | 0 | 0 | 91980 | 9500 | 0 | -48804.98 | 101480 | 52675.02 | 1 | 0.51907 | 0 | 0.51907 | 0 | 0.51907 | 0 | 0.51907 | 48804.98 | 1 | 52675.02 |  | 52675.02 | 101480 | 0 | 0 | 0 | 101480 | 52675.02 | 0 | 0 | 0 | 0 | 0 | 101480 | 0 | 0 | 2021-12-31
21-1017- | CT DOT 0154-0125 - ARBORIO CORP | ARBORIO COROPORATION |  |  | CONNECTICUT | Y | 352000 | 33812.04 | 0 |  | 385812.04 | 219653.46 | 287820 | 24384.98 | 64180 | 9427.06 | 312204.98 | 92551.52 | 73607.06 | 166158.58 | 0.19078 | 0.43067 | 0.80922 | -0.37854 | 0.80922 | -0.37854 | 0.80922 | -0.37854 | 219653.46 | 1 | 166158.58 |  | 166158.58 | 385812.04 | 0 | 0 | 0 | 385812.04 | 166158.58 | 0 | 0 | 0 | 0 | 0 | 385812.04 | 10458.67 | 0 | 2023-09-06
21-1018- | HUNT'S POINT - DEAN ENERGY SOLUTIONS | DEAN ENERGY SOLUTIONS |  |  | NEW YORK | Y | 30000 | 0 | 0 |  | 30000 | 15209.84 | 21000 | 0 | 9000 | 0 | 21000 | 5790.16 | 9000 | 14790.16 | 0.3 | 0.49301 | 0.7 | -0.20699 | 0.7 | -0.20699 | 0.7 | -0.20699 | 15209.84 | 1 | 14790.16 |  | 14790.16 | 30000 | 0 | 0 | 0 | 30000 | 14790.16 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 2023-12-07
21-1020- | NY 17-530 REHAB VARIOUS BRIDGES WESTCHESTER - LAURA | LAURA LI INDUSTRIES |  |  | NEW YORK | Y | 133850 | 400 | 0 |  | 134250 | 21695.28 | 100850 | 0 | 33000 | 400 | 100850 | 79154.72 | 33400 | 112554.72 | 0.24879 | 0.8384 | 0.75121 | 0.087186 | 0.75121 | 0.087186 | 0.75121 | 0.087186 | 21695.28 | 1 | 112554.72 |  | 112554.72 | 134250 | 0 | 0 | 0 | 134250 | 112554.72 | 0 | 0 | 0 | 0 | 0 | 134250 | 0 | 0 | 2023-12-07
22-1001- | CRANES AT HOLTSVILLE GT - NATIONAL GRID | National Grid |  |  | NEW YORK | Y | 141400 | -8000 | 0 |  | 133400 | 201907.89 | 120190 | 0 | 21210 | -8000 | 120190 | -81717.89 | 13210 | -68507.89 | 0.099025 | -0.51355 | 0.90097 | -1.4145 | 0.90097 | -1.4145 | 0.90097 | -1.4145 | 201907.89 | 1 | -68507.89 |  | -68507.89 | 133400 | 0 | 0 | 0 | 133400 | -68507.89 | 0 | 0 | 0 | 0 | 0 | 133400 | 6300.34 | 0 | 2023-09-06
22-1002- | H-STREET BRIDGE REHABILITATION - MCNAMEE - PV | McNamee Construction Corp. |  |  | NEW YORK | Y | 51625 | 0 | -1475 |  | 50150 | 19522.76 | 43300 | 0 | 8325 | 0 | 43300 | 23777.24 | 6850 | 30627.24 | 0.13659 | 0.61071 | 0.83874 | -0.22803 | 0.83874 | -0.22803 | 0.83874 | -0.22803 | 19522.76 | 1 | 30627.24 |  | 30627.24 | 50150 | 0 | 0 | 0 | 50150 | 30627.24 | 0 | 0 | 0 | 0 | 0 | 50150 | 0 | 0 | 2025-03-18
22-1005- | RI DOT / #2022CB046 / AETNA BRIDGE CO. | Aetna Bridge Company |  |  | RHODE ISLAND | Y | 855500 | 0 | 0 |  | 855500 | 489122.54 | 641250 | 0 | 214250 | 0 | 641250 | 152127.46 | 214250 | 366377.46 | 0.25044 | 0.42826 | 0.74956 | -0.3213 | 0.74956 | -0.3213 | 0.74956 | -0.3213 | 489122.54 | 1 | 366377.46 |  | 366377.46 | 855500 | 0 | 0 | 0 | 855500 | 366377.46 | 0 | 0 | 14380.08 | 27862.5 | 0 | 855500 | 19110.03 | 0 | 2025-03-18
22-1007- | RFK BRIDGE / COMMODORE MAINT. | COMMODORE MAINTENANCE CORP |  |  | NEW YORK | Y | 1850000 | 0 | 0 |  | 1850000 | 1678795.86 | 1354000 | 0 | 496000 | 0 | 1354000 | -324795.86 | 496000 | 171204.14 | 0.26811 | 0.092543 | 0.73189 | -0.63935 | 0.73189 | -0.63935 | 0.73189 | -0.63935 | 1678795.86 | 1 | 171204.14 |  | 171204.14 | 1850000 | 0 | 0 | 0 | 1850000 | 171204.14 | 0 | 0 | 0 | 0 | 0 | 1850000 | 72155.75 | 0 | 2025-03-18
22-1095- | BRIDGE PAINTING OF SEVEN BRIDGES - CMC - PETER | COMMODORE MAINTENANCE CORP |  |  | NEW YORK | Y | 288000 | 0 | 0 |  | 288000 | 421130.4 | 240000 | 0 | 48000 | 0 | 240000 | -181130.4 | 48000 | -133130.4 | 0.16667 | -0.46226 | 0.83333 | -1.2956 | 0.83333 | -1.2956 | 0.83333 | -1.2956 | 421130.4 | 1 | -133130.4 |  | -133130.4 | 288000 | 0 | 0 | 0 | 288000 | -133130.4 | 0 | 0 | 0 | 0 | 0 | 288000 | 0 | 0 | 2025-03-18
23-1001- | NYPA COOLING TOWER / MACAN DEVE | MACAN DEVE ENGINEERS, DPC |  |  | NEW YORK | Y | 126000 | 1425 | 0 |  | 127425 | 63404.37 | 72500 | 0 | 53500 | 1425 | 72500 | 9095.63 | 54925 | 64020.63 | 0.43104 | 0.50242 | 0.56896 | -0.066544 | 0.56896 | -0.066544 | 0.56896 | -0.066544 | 63404.37 | 1 | 64020.63 |  | 64020.63 | 127425 | 0 | 0 | 0 | 127425 | 64020.63 | 0 | 0 | 4623.03 | 1425 | 0 | 127425 | 0 | 0 | 2025-03-18
Grand Totals:
[5 empty] | Department Totals: | Department | Costs and Estimated Earnings In Excess Of Billings
[6 empty] | CONNECTICUT | SUM from above
[6 empty] | MASSACHUSETTS | SUM from above
[6 empty] | NEW YORK | SUM from above
[6 empty] | RHODE ISLAND | SUM from above

## Active
#VALUE!
Active
For The Period Ended 2025-03-31
Count of Jobs: | 22
Job # | Contract | Customer | Project Manager | Estimator | Department | Closed Status | Base Contract | Approved Change Orders | (Work Done ) Outstanding Change Orders | Outstanding Allowance | Adjusted Contract Price | Estimated Total Direct Costs | QU Original Budget | CO Change Order Budget | Original GP | Change Order GP | Total Direct Budget | Over/Under Budget | Budgeted Gross Profit (Loss) | Estimated Gross Profit (Loss) | Estimated GP % | Current GP % | Prior Month1 GP | Variance Month1 GP | Prior Month2 GP | Variance Month2 GP | Prior Month3 GP | Variance Month3 GP | Direct Cost To Date | % Complete | Total Gross Profit Recognized To Date | Gross Profit Recognized Prior Years | Gross Profit (Loss) Recognized This Year | Total Amount Billed To Date | Remaining Billing Amount | Current Retainage Amount | Retainage % Held | Cash Received | Net Cash Flow | Costs and Estimated Earnings In Excess Of Billings | Billings In Excess Of Costs And Estimated Earnings | Prior Year Incurred Cost | Prior Year Billing | AR | AR Retainage | AP | AP Retainage | Last Projection Date
21-1009- | HT.224.130 HOLLAND TUNNEL / TULLY CONST. | Tully Construction Co., Inc. |  |  | NEW YORK | N | 2730505 | 196964.64 | -1248326.64 |  | 1679143 | 1627144.05 | 2243954.42 | 78928 | 486550.58 | 118036.64 | 2322882.42 | 695738.37 | -643739.42 | 51998.95 | -0.38337 | 0.030968 | 0.79348 | -0.76251 | 0.79348 | -0.76251 | 0.79348 | -0.76251 | 1627143.41 | 1 | 51998.9295 |  | 51998.9295 | 1679142.74 | 0.26 | 83957.15 | 0.05 | 1579603.6 | -47539.81 | 0 | 0.40045 | 1103808.57 | 901423.78 | 15581.99 | 1579603.6 | 186.24 | 0 | 2025-03-18
21-1021- | MA DOT #117036 - Interstate 90 Bridges - MIG CORP. | MIG CORPORATION, INC. |  |  | MASSACHUSETTS | N | 1200000 | 45671.02 | 0 |  | 1245671.02 | 1688209.91 | 1020000 | 28621.07 | 180000 | 17049.95 | 1048621.07 | -639588.84 | 197049.95 | -442538.89 | 0.15819 | -0.35526 | 0.84181 | -1.1971 | 0.83138 | -1.1866 | 0.83138 | -1.1866 | 1688209.37 | 1 | -442538.7484 |  | -442538.7484 | 1245671.02 | 0 | 0 | 0 | 1245671.02 | -442538.35 | 0 | 0.39845 | 59148.28 | 45671.02 | 0 | 1245671.02 | 94145.76 | 0 | 2024-12-31
22-1004- | CT DOT 0040-0141 / HADDAM / AMER. BRDGE. | American Bridge Co. |  |  | CONNECTICUT | N | 3102105.09 | 718853.93 | -262482.02 |  | 3558477 | 3519005 | 2288568 | 741524.5 | 813537.09 | -22670.57 | 3030092.5 | -488912.5 | 528384.5 | 39472 | 0.14849 | 0.011092 | 0.79302 | -0.78193 | 0.79302 | -0.78193 | 0.79302 | -0.78193 | 3520412.13 | 1.0004 | 39487.7835 |  | 39487.7835 | 3765599.02 | -207122.02 | 0 | 0 | 3411940.84 | -108471.29 | 0 | 205699.1065 | 905314.35 | 856319.02 | 353658.18 | 3411940.84 | 206943.06 | 0 | 2024-12-31
22-1006- | CT DOT 165-509 / WINDSOR LOCKS / ROTHA | Rotha Contracting Co., Inc. |  |  | CONNECTICUT | N | 2228730 | 66000 | -508089.63 |  | 1786640.37 | 2264015 | 1760000 | 0 | 468730 | 66000 | 1760000 | -504015 | 26640.37 | -477374.63 | 0.014911 | -0.26719 | 0.76697 | -1.0342 | 0.76697 | -1.0342 | 0.76697 | -1.0342 | 2264014.11 | 1 | -477374.4423 |  | -477374.4423 | 1786640.37 | 0 | 0 | 0 | 1786640.37 | -477373.74 | 0 | 0.70234 | 907599.82 | 556300.57 | 0 | 1786640.37 | 72099.84 | 0 | 2024-12-31
22-1008- | CT DOT 170-3557 / MCNAMEE | McNamee Construction Corp. |  |  | CONNECTICUT | N | 1450000 | -149294.02 | -204705.98 |  | 1096000 | 746280 | 987000 | -90720 | 463000 | -58574.02 | 896280 | 150000 | 199720 | 349720 | 0.18223 | 0.31909 | 0.68907 | -0.36998 | 0.68907 | -0.36998 | 0.68907 | -0.36998 | 644620.89 | 0.86378 | 302080.744 |  | 302080.744 | 896055.98 | 199944.02 | 0 | 0 | 861555.98 | 216935.09 | 50645.654 | 0 | 192848.27 | 182555.98 | 34500 | 861555.98 | 5805.93 | 0 | 2024-08-05
22-1009- | CT DOT 170-3551 / ROTHA | Rotha Contracting Co., Inc. |  |  | CONNECTICUT | N | 712300 | 0 | 0 |  | 712300 | 530000 | 530000 | 0 | 182300 | 0 | 530000 | 0 | 182300 | 182300 | 0.25593 | 0.25593 | 0.74407 | -0.48814 | 0.74407 | -0.48814 | 0.74407 | -0.48814 | 241600.33 | 0.45585 | 83101.3965 |  | 83101.3965 | 389990 | 322310 | 0 | 0 | 389990 | 148389.67 | 0 | 65288.2735 | 160876.8 | 190990 | 0 | 389990 | 10209.83 | 0 | 2023-06-27
22-1010- | CT DOT 0171-0484 / BEAM END REPAIRS / MCNAMEE | McNamee Construction Corp. |  |  | CONNECTICUT | N | 1408029.65 | 132225.95 | -130594.6 |  | 1409661 | 1005000 | 1005000 | 49160 | 403029.65 | 83065.95 | 1054160 | 49160 | 355501 | 404661 | 0.25219 | 0.28706 | 0.68441 | -0.39734 | 0.68441 | -0.39734 | 0.68441 | -0.39734 | 966987.34 | 0.96218 | 389355.2876 |  | 389355.2876 | 1419311.2 | -9650.2 | 0 | 0 | 1380347.55 | 413360.21 | 0 | 62968.5724 | 628830.78 | 948977.45 | 38963.65 | 1380347.55 | 10139.68 | 0 | 2023-06-27
23-1000- | NYC DOT HB1070QN / BREWER & CROSS BAY / COMMODORE | COMMODORE CONSTRUCTION CORP |  |  | NEW YORK | N | 2300000 | 0 | 0 |  | 2300000 | 2186175 | 1910000 | 0 | 390000 | 0 | 1910000 | -276175 | 390000 | 113825 | 0.16957 | 0.049489 | 0.83043 | -0.78094 | 0.83043 | -0.78094 | 0.83043 | -0.78094 | 2186267.51 | 1 | 113829.8166 |  | 113829.8166 | 1546448.32 | 753551.68 | 0 | 0 | 442000 | -1744267.51 | 753649.0066 | 0 | 1419528.04 | 1305388.29 | 1104448.32 | 442000 | 226809.48 | 0 | 2025-03-13
23-1002- | MA DOT #122517 - TEWKSBURY - NEL CORP. | NEL Corp. |  |  | MASSACHUSETTS | N | 2416210 | 0 | 0 |  | 2416210 | 1720948 | 1720948 | 0 | 695262 | 0 | 1720948 | 0 | 695262 | 695262 | 0.28775 | 0.28775 | 0.71225 | -0.4245 | 0.71225 | -0.4245 | 0.71225 | -0.4245 | 44375.77 | 0.025786 | 17927.7855 |  | 17927.7855 | 0 | 2416210 | 0 | 0 | 0 | -44375.77 | 62303.5555 | 0 | 6895.2 | 0 | 0 | 0 | 5135 | 0 | 2024-08-02
24-1001- | RK-19A / CMC / RFK BRIDGE PLATFORM | COMMODORE MAINTENANCE CORP |  |  | NEW YORK | N | 13700000 | -3700000 | 0 |  | 10000000 | 6621980 | 6621980 | 0 | 7078020 | -3700000 | 6621980 | 0 | 3378020 | 3378020 | 0.3378 | 0.3378 | 0.6622 | -0.3244 | 0.6622 | -0.3244 | 0.6622 | -0.3244 | 3925459.68 | 0.59279 | 2002464.7172 |  | 2002464.7172 | 6078005 | 3921995 | 0 | 0 | 5799000 | 1873540.32 | 0 | 150080.6028 | 3517103.89 | 5702625 | 279005 | 5799000 | 90363.41 | 0 | 2025-03-25
24-1002- | NYC DDC / HWK1669A / JRCRUZ | JRCRUZ Corp. |  |  | NEW YORK | N | 617796 | 0 | 0 |  | 617796 | 94567.41 | 368315.2 | 0 | 249480.8 | 0 | 368315.2 | 273747.79 | 249480.8 | 523228.59 | 0.40382 | 0.84693 | 0.59618 | 0.25075 | 0.59618 | 0.25075 | 0.59618 | 0.25075 | 94567.55 | 1 | 523229.3646 |  | 523229.3646 | 617796 | 0 | 0 | 0 | 533516.39 | 438948.84 | 0.9146 | 0 | 90229.19 | 617796 | 84279.61 | 533516.39 | 18018.21 | 0 | 2025-03-13
24-1003- | RI DOT 2024CB018 / AETNA BRIDGE / LAFAYETTE BRIDGE REPAIRS | Aetna Bridge Company |  |  | RHODE ISLAND | N | 513955.56 | 0 | 0 |  | 513955.56 | 300409.78 | 300409.78 | 0 | 213545.78 | 0 | 300409.78 | 0 | 213545.78 | 213545.78 | 0.41549 | 0.41549 | 0.58451 | -0.16901 | 0.58451 | -0.16901 | 0.58451 | -0.16901 | 54454.99 | 0.18127 | 38709.2368 |  | 38709.2368 | 262966.58 | 250988.98 | 0 | 0 | 252318.34 | 197863.35 | 0 | 169802.3532 | 54439.79 | 262966.58 | 10648.24 | 252318.34 | 3917.92 | 0 | 2025-03-13
24-1004- | Emergency Repairs / Willimantic | McNamee Construction Corp. |  |  | CONNECTICUT | N | 251517.42 | 0 | -161517.42 |  | 90000 | 52830.48 | 183260 | 0 | 68257.42 | 0 | 183260 | 130429.52 | -93260 | 37169.52 | -1.0362 | 0.41299 | 0.72862 | -0.31562 | 0.72862 | -0.31562 | 0.72862 | -0.31562 | 52829.68 | 0.99998 | 37168.9572 |  | 37168.9572 | 150910.45 | -60910.45 | 0 | 0 | 0 | -52829.68 | 0 | 60911.8128 | 48215.13 | 150910.45 | 150910.45 | 0 | 5698.73 | 0 | 2025-03-13
24-1005- | CT DOT 0015-0339 / BRIDGE #02475 / BRIDGEPORT / MOHAWK | Mohawk Northeast, Inc. |  |  | CONNECTICUT | N | 3985840 | 0 | 0 |  | 3985840 | 3149649 | 3149649 | 0 | 836191 | 0 | 3149649 | 0 | 836191 | 836191 | 0.20979 | 0.20979 | 0.79021 | -0.58042 | 0.79021 | -0.58042 | 0.79021 | -0.58042 | 6570.14 | 0.002086 | 1744.287 |  | 1744.287 | 159434 | 3826406 | 0 | 0 | 159434 | 152863.86 | 0 | 151119.573 | 0 | 0 | 0 | 159434 | 6410 | 0 | 2025-02-01
25-1000- | CT DOT 0053-0196 / ROUTE 2, GLASTONBURY / MCNAMEE | McNamee Construction Corp. |  |  | CONNECTICUT | N | 2105000 | 0 | 0 |  | 2105000 | 1679195 | 1679195 | 0 | 425805 | 0 | 1679195 | 0 | 425805 | 425805 | 0.20228 | 0.20228 | 0.79772 | -0.59543 | 0.79772 | -0.59543 | 0 | 0.20228 | 2500 | 0.0014888 | 633.9422 |  | 633.9422 | 84200 | 2020800 | 0 | 0 | 0 | -2500 | 0 | 81066.0578 | 0 | 0 | 84200 | 0 | 2500 | 0 | 2025-02-01
25-1001- | CT DOT CHURCH ST / MCNAMEE | McNamee Construction Corp. |  |  | CONNECTICUT | N | 177500 | 0 | -177500 |  | 0 | 0 | 138963.62 | 0 | 38536.38 | 0 | 138963.62 | 138963.62 | -138963.62 | 0 | 0 | 0 | 0.78289 | -0.78289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 7100 | -7100 | 0 | 0 | 0 | 0 | 0 | 7100 | 0 | 0 | 7100 | 0 | 0 | 0
CT- - | CT Template |  |  |  | CONNECTICUT | N | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MA- - | MA Template |  |  |  | MASSACHUSETTS | N | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MO- - | MO Template |  |  |  | MISSOURI | N | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NJ- - | NJ Template |  |  |  | NEW JERSEY | N | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NY- - | NY Template |  |  |  | NEW YORK | N | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RI- - | RI Template |  |  |  | RHODE ISLAND | N | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Totals: